## READ ME
New Excel Bidding Spreadsheet: How It Works
Rebuilt from 'Template-Empty - WORK IN PROGRESS.xlsm'. Full transparent cost first, margin added on top.
FLOW
| 1. INPUTS | Project info, durations, PST, consumables, contingency, target margin per division, levels, your typical COGS %.
| 2. LABOUR RATES | Crew mix per trade (same layout as the original PRJ INFO rates block), shown beside Knowify actual rates and mix.
| 3. PLUMBING EST / HVAC EST | One row per item: Qty x Material $/unit and Qty x Hrs/unit. Same columns on both sheets so HVAC ties back exactly like Plumbing.
| 4. SUBS & GC | Subtrade quotes and general conditions. Allocate by % to each division, or leave % blank to auto-split by direct cost.
| 5. BID SUMMARY | Cost by type and division, then margin. COGS mix vs your Knowify job and vs your typical %. Holds every tie-out check.
| 6. BUDGET | Cost budget per division and phase. Phases match Knowify, so the field budget and the actuals line up.
| 7. SCHEDULE OF VALUES | Contract split into Knowify-style lines (e.g. 'P - BLDG A - L1 Plumbing Rough-in (Labour)'), with the Knowify cost budget for each line.
| 8. KNOWIFY PHASES / TIME | Paste the 'Actual vs Budget - Phases' and 'Time' sheets from a Knowify Job Summary export, cell A1, exactly as exported.
| 9. KNOWIFY REVIEW | Reads the two paste tabs: margin after overhead, cost mix, actual crew rates and mix, and how each phase ran vs its budget.
| 10. AUDIT NOTES | Formula problems found in the original template, decisions made, and open questions.
COLOUR LEGEND
| Blue text, light yellow fill | Input. Type here.
| Bright yellow fill | Key assumption. Review on every bid.
| Black text | Formula. Do not type over.
| Green text | Link from another tab.
MARGIN vs MARKUP
This workbook prices with MARGIN: Contract = Total Cost / (1 - Margin %).
Example: cost $100,000 at 15% margin = $117,647 contract, $17,647 gross profit (17.6% markup).
The original template used 15% MARKUP: $100,000 x 1.15 = $115,000, which is only a 13.0% margin.
PHASES (match Knowify)
Tag each estimate row with the phase the WORK happens in. Rough-in and finishing rows carry both labour and material.
Labour on 03 Rough-in and 04 Finishing is split by level on the SOV; their material rolls into 05 Material Supply automatically,
the same way Knowify jobs are set up (level lines are labour only, material supply is its own line).
UPDATING KNOWIFY DATA
1. In Knowify, open the job > Summary > Project Summary report and download the Excel file.
2. In that file, select the used cells of 'Actual vs Budget - Phases' (A1 to column V, last row). Copy.
3. Paste into cell A1 of KNOWIFY PHASES (clear old data first). Do the same for the 'Time' sheet into KNOWIFY TIME.
4. On KNOWIFY REVIEW, type the job name, contract (Total Amount) and committed cost from the export's Summary sheet.
5. If a role or phase shows 'Unmapped', add it to the mapping tables on the right of KNOWIFY REVIEW.

## INPUTS
INPUTS
Blue cells are inputs. Bright yellow = key assumption to review on every bid.
PROJECT INFORMATION
Project Name
Quote Number
| Project Type | Multi-Family
Owner
General Contractor
Architect
Mech. Engineer
| Site Address | 2650 East 41st Ave
| City | Vancouver
Proposal Date
Proposal Rev
| Prepared By | Paris Mechanical Ltd
| Drawings | Issued For Tender
Gross Floor Area (sq ft)
| Number of Units | 123
KEY ASSUMPTIONS
| P&H project duration (months) | 24 |  |  |  | From original PRJ INFO H34.
| HVAC project duration (months) | 24 |  |  |  | From original PRJ INFO H43.
| PST on materials | 7% |  |  |  | BC PST 7%. From original PRJ INFO H52. Applied to material rows marked Y.
| GST (shown on proposal only, not a cost) | 5% |  |  |  | From original PRJ INFO H51. GST is recoverable, so it is not in cost.
| Consumables (% of material) | 2% |  |  |  | Original used 2% of material (P&H SUMMARY H46, HVAC SUMMARY D30).
| Contingency (% of direct cost) | 0% |  |  |  | Optional risk allowance. Kept as its own line so it stays visible.
| Warranty reserve (% of fixture & equipment supply) | 2% |  |  |  | Original: 2 years x 1% of equipment+fixtures (PRJ SUMMARY rows 75-78).
| Contract rounding (round up to nearest $) | 100 |  |  |  | Original rounded each division up to the nearest $100.
| Holdback (BC Builders Lien Act) | 10% |  |  |  | Used on the SOV for progress billing.
TARGET MARGIN BY DIVISION
| Division | Code | Target Margin % | Equivalent Markup % | Crew
| Plumbing | P | 15% | 17.65% | P&H | Margin = profit / contract. 15% is a placeholder: set your real target.
| Hydronic | H | 15% | 17.65% | P&H | Division names feed the SOV line names (Knowify uses 'HVAC'
| Ventilation | V | 15% | 17.65% | HVAC | for ventilation; rename here if you prefer that).
| Air Conditioning | AC | 15% | 17.65% | HVAC
LEVELS (SOV splits rough-in and finishing labour by level)
| Tag (e.g. BLDG A - L1) | Floor | Units | SOV Weight %
| U/G | Ground Work |  | 0% |  | Units per level from original PRJ INFO C6:C10.
| P-02 | Parking 2 |  | 0% |  | Weight defaults to units share. Type over it to give parking,
| PRKG | Parking 1 |  | 0% |  | U/G or roof a share. Weights must total 100%.
| L-01 | Level 1 | 24 | 19.51% |  | Multi-building jobs: use tags like 'BLDG A - L1' to match Knowify.
| L-02 | Level 2 | 25 | 20.33%
| L-03 | Level 3 | 25 | 20.33%
| L-04 | Level 4 | 25 | 20.33%
| L-05 | Level 5 | 24 | 19.51%
| L-06 | Level 6 |  | 0%
| L-07 | Level 7 |  | 0%
| L-08 | Level 8 |  | 0%
| L-09 | Level 9 |  | 0%
| L-10 | Level 10 |  | 0%
| ROOF | Roof |  | 0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
| TOTAL |  | 123 | 100% | OK
PHASES (drop-down list used on every tab; matches Knowify setup)
| 01 Shop Drawings, Permits & Mobilization |  |  |  |  | Rename freely but keep 9 rows and keep the order:
| 02 Foundation & Underground |  |  |  |  | 03/04 are split by level; 05 collects 03/04 material.
03 Rough-in (Labour)
04 Finishing (Labour)
05 Material Supply
06 Fixtures & Equipment Supply
07 Testing, TAB & Commissioning
08 Completion & Final Documents
09 Office, Supervision & General
YOUR TYPICAL COST OF GOODS (% of total cost)
| Cost Type | Typical % of Total Cost
| Labour (wage + burden) |  |  |  |  | Leave blank if unknown; BID SUMMARY compares only filled rows.
Overhead
| Material: pipe, fittings, valves (incl. PST + consumables) | 26% |  |  |  | 26% of total COGS: from estimator (Oct 2026). On 405 Marie Place, material
| Fixtures & Equipment Supply |  |  |  |  | excluding fixtures & equipment supply was 25.9% of cost.
Subtrades
General Conditions
Contingency
| TOTAL | 26%

## LABOUR RATES
LABOUR RATES (crew mix)
Same layout as the original PRJ INFO rates block. Both trades tie back the same way. | UPDATED 2026-06-29
PLUMBING & HYDRONIC CREW
| Classification | Burdened Rate $/hr | Crew Mix % | Weighted $/hr | Hours | Cost by Wage Breakdown | Knowify Actual $/hr | Knowify Actual Mix
| Apprentice Lvl 1-2 | 53 | 40% | 21.2 | 590.4 | 31291.2 | 40.2489 | 36.47% | Rates are fully burdened (confirmed): from original PRJ INFO D36:D40.
| Apprentice Lvl 3-6 | 62.5 | 30% | 18.75 | 442.8 | 27675 | 47.1021 | 24.98% | Crew mix from original PRJ INFO E36:E40.
| Apprentice Lvl 7-8 | 66.5 | 5% | 3.325 | 73.8 | 4907.7 | 51.213 | 8.578% | Overhead $22/hr from original PRJ INFO H35/H44 (salaried staff, company wide).
| Journeyman Lvl 1-2 | 73 | 11% | 8.03 | 162.36 | 11852.28 | 61.5465 | 12.01% | Knowify columns: company-wide actuals from KNOWIFY TIME (all trades together).
| Foreman & PM | 96 | 14% | 13.44 | 206.64 | 19837.44 | 68.3354 | 17.96% | Knowify mix excludes 'Unmapped' roles, so it can total under 100%.
| Weighted average burdened wage |  | 100% | 64.745 | 1476 | 95563.62 | 50.5027 | 100%
| Overhead $/hr (salaried staff, shop, office, insurance) | 22
| FULLY LOADED RATE $/hr | 86.745
| Crew mix = 100% and hours x rate ties to breakdown | OK
| Estimated hours (from estimate tabs) | 1476
HVAC CREW (ventilation & A/C)
| Classification | Burdened Rate $/hr | Crew Mix % | Weighted $/hr | Hours | Cost by Wage Breakdown | Knowify Actual $/hr | Knowify Actual Mix
| Apprentice Lvl 1-2 | 53 | 40% | 21.2 | 0 | 0 | 40.2489 | 36.47% | Rates are fully burdened (confirmed): from original PRJ INFO D36:D40.
| Apprentice Lvl 3-6 | 62.5 | 30% | 18.75 | 0 | 0 | 47.1021 | 24.98% | Crew mix from original PRJ INFO E36:E40.
| Apprentice Lvl 7-8 | 66.5 | 5% | 3.325 | 0 | 0 | 51.213 | 8.578% | Overhead $22/hr from original PRJ INFO H35/H44 (salaried staff, company wide).
| Journeyman Lvl 1-2 | 73 | 11% | 8.03 | 0 | 0 | 61.5465 | 12.01% | Knowify columns: company-wide actuals from KNOWIFY TIME (all trades together).
| Foreman & PM | 96 | 14% | 13.44 | 0 | 0 | 68.3354 | 17.96% | Knowify mix excludes 'Unmapped' roles, so it can total under 100%.
| Weighted average burdened wage |  | 100% | 64.745 | 0 | 0 | 50.5027 | 100%
| Overhead $/hr (salaried staff, shop, office, insurance) | 22
| FULLY LOADED RATE $/hr | 86.745
| Crew mix = 100% and hours x rate ties to breakdown | OK
| Estimated hours (from estimate tabs) | 0
RATE COMPARISON (per hour)
| Rate Basis | $/hr |  |  | P&H Est. Hours | Labour (+OH) Cost
| Original template line items (Apprentice 1-2 only) | 53 |  |  | 1476 | 78228 |  |  | If Knowify's cost per hour is well below the template rate, either Knowify
| Original template 'Budget with' (simple average) | 70.2 |  |  | 1476 | 103615.2 |  |  | is missing burden, or the template rates are high. Settle which is true
| Crew-mix weighted burdened wage (this template) | 64.745 |  |  | 1476 | 95563.62 |  |  | before trusting either for bids.
| Fully loaded: weighted wage + overhead | 86.745 |  |  | 1476 | 128035.62
| Knowify actual average cost per hour (job pasted) | 50.5027 |  |  | 1476 | 74541.9961
| Knowify actual + overhead | 72.5027 |  |  | 1476 | 107013.9961

## PLUMBING EST
PLUMBING EST
Plumbing (P) and Hydronic (H). Seed unit costs and hours from the original EQUIPMENT sheet.
TOTALS | [10 empty] | 105288 | 1476 | 95563.62 | 32472 | 233323.62
Labour $ = Hours x crew-mix weighted burdened wage. Overhead $ = Hours x overhead $/hr. P/H rows use the P&H crew, V/AC rows use the HVAC crew. Q:R show how the same Div + Phase ran vs budget on the Knowify job pasted (1.30x = 30% over).
Item Code | Div | Phase | Description | Qty | Unit | Material $/Unit | Hrs/Unit | Add Material $ | Add Hrs | PST? (Y/N) | Material $ (incl PST) | Hours | Labour $ (wage+burden) | Overhead $ | TOTAL COST $ | Knowify Labour Actual/Budget | Knowify Material Actual/Budget | History Flag
P-UG-SUMP | P | 02 Foundation & Underground | Sumps & Interceptors |  | ea |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0 | 1.7293 | 1.022 | Past job ran over budget
P-UG-STRM | P | 02 Foundation & Underground | Storm Water & Drain Tile |  | lf |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0 | 1.7293 | 1.022 | Past job ran over budget
P-UG-SAN | P | 02 Foundation & Underground | Sanitary (underground) |  | lf |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0 | 1.7293 | 1.022 | Past job ran over budget
P-UG-DW | P | 02 Foundation & Underground | Domestic Water (underground) |  | lf |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0 | 1.7293 | 1.022 | Past job ran over budget
P-RI-STRM | P | 03 Rough-in (Labour) | DWV Storm Water |  | lf |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0 | 1.3492 | 1.2924 | Past job ran over budget
P-RI-SAN | P | 03 Rough-in (Labour) | DWV Sanitary (Drainage/Vents) |  | lf |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0 | 1.3492 | 1.2924 | Past job ran over budget
P-RI-WR2 | P | 03 Rough-in (Labour) | 2-Piece Bathroom (WC, LAV) |  | ea | 550 | 3 |  |  | Y | 0 | 0 | 0 | 0 | 0 | 1.3492 | 1.2924 | Past job ran over budget
P-RI-WR3T | P | 03 Rough-in (Labour) | 3-Piece Bathroom (WC, LAV, TUB) |  | ea | 860 | 5 |  |  | Y | 0 | 0 | 0 | 0 | 0 | 1.3492 | 1.2924 | Past job ran over budget
P-RI-WR3S | P | 03 Rough-in (Labour) | 3-Piece Bathroom (WC, LAV, SH) |  | ea | 860 | 5 |  |  | Y | 0 | 0 | 0 | 0 | 0 | 1.3492 | 1.2924 | Past job ran over budget
P-RI-WR4T | P | 03 Rough-in (Labour) | 4-Piece Bathroom (WC, 2LAV, TUB) |  | ea | 990 | 6 |  |  | Y | 0 | 0 | 0 | 0 | 0 | 1.3492 | 1.2924 | Past job ran over budget
P-RI-WR4S | P | 03 Rough-in (Labour) | 4-Piece Bathroom (WC, 2LAV, SH) |  | ea | 990 | 6 |  |  | Y | 0 | 0 | 0 | 0 | 0 | 1.3492 | 1.2924 | Past job ran over budget
P-RI-WR4TS | P | 03 Rough-in (Labour) | 4-Piece Bathroom (WC, LAV, TUB & SH) |  | ea | 1310 | 6 |  |  | Y | 0 | 0 | 0 | 0 | 0 | 1.3492 | 1.2924 | Past job ran over budget
P-RI-WR5 | P | 03 Rough-in (Labour) | 5-Piece Bathroom (WC, 2LAV, TUB & SH) |  | ea | 1460 | 6 |  |  | Y | 0 | 0 | 0 | 0 | 0 | 1.3492 | 1.2924 | Past job ran over budget
P-RI-LAUN | P | 03 Rough-in (Labour) | Laundry - 4" Wet Vent |  | ea | 280 | 2 |  |  | Y | 0 | 0 | 0 | 0 | 0 | 1.3492 | 1.2924 | Past job ran over budget
P-RI-KS3 | P | 03 Rough-in (Labour) | Kitchen Sink - 3" Vent |  | ea | 240 | 2 |  |  | Y | 0 | 0 | 0 | 0 | 0 | 1.3492 | 1.2924 | Past job ran over budget
P-RI-KS4 | P | 03 Rough-in (Labour) | Kitchen Sink - 4" Vent |  | ea | 250 | 2 |  |  | Y | 0 | 0 | 0 | 0 | 0 | 1.3492 | 1.2924 | Past job ran over budget
P-RI-DWD | P | 03 Rough-in (Labour) | Domestic Water Distribution Piping |  | lf |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0 | 1.3492 | 1.2924 | Past job ran over budget
P-RI-DWS | P | 03 Rough-in (Labour) | Domestic Water Insuite Piping | 123 | suite | 800 | 12 |  |  | Y | 105288 | 1476 | 95563.62 | 32472 | 233323.62 | 1.3492 | 1.2924 | Past job ran over budget
P-RI-IRR | P | 03 Rough-in (Labour) | Irrigation |  | LS |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0 | 1.3492 | 1.2924 | Past job ran over budget
P-RI-COND | P | 03 Rough-in (Labour) | Condensate Drains (if by Plumbing) |  | LS |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0 | 1.3492 | 1.2924 | Past job ran over budget
P-RI-GAS | P | 03 Rough-in (Labour) | Gas & Boiler Vents |  | LS |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0 | 1.3492 | 1.2924 | Past job ran over budget
P-RI-DRN | P | 03 Rough-in (Labour) | Drains & Hose Bibs (rough-in) |  | ea |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0 | 1.3492 | 1.2924 | Past job ran over budget
P-RI-WER | P | 03 Rough-in (Labour) | Water Entry Room |  | LS |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0 | 1.3492 | 1.2924 | Past job ran over budget
P-RI-FLSH | P | 03 Rough-in (Labour) | Roof Flashings |  | ea |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0 | 1.3492 | 1.2924 | Past job ran over budget
P-RI-CAN | P | 03 Rough-in (Labour) | Canning / Cutting / Layout |  | LS |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0 | 1.3492 | 1.2924 | Past job ran over budget
P-RI-CLN | P | 03 Rough-in (Labour) | Clean-up |  | LS |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0 | 1.3492 | 1.2924 | Past job ran over budget
P-FN-FIX | P | 04 Finishing (Labour) | Set Plumbing Fixtures |  | ea |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0 |  | 1.2924 | Past job ran over budget
P-FN-AP | P | 04 Finishing (Labour) | Install Access Panels |  | ea |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0 |  | 1.2924 | Past job ran over budget
P-FN-LBL | P | 04 Finishing (Labour) | Pipe Labelling |  | LS |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0 |  | 1.2924 | Past job ran over budget
P-EQ-FIX | P | 06 Fixtures & Equipment Supply | Plumbing Fixtures & Access Panels Supply |  | LS |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0
P-EQ-DRN | P | 06 Fixtures & Equipment Supply | Drains Supply (FD, AD, RD, HB, TD, TP) |  | LS |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0
P-EQ-EQP | P | 06 Fixtures & Equipment Supply | Mech Room & Equipment Supply (DHW, pumps, tanks) |  | LS |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0
P-TS-TEST | P | 07 Testing, TAB & Commissioning | Testing |  | LS |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0
P-CL-DOCS | P | 08 Completion & Final Documents | As-builts, O&M, Closeout |  | LS |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0
H-UG-PIPE | H | 02 Foundation & Underground | Hydronic U/G Piping |  | lf |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0
H-RI-DIST | H | 03 Rough-in (Labour) | Heating Distribution Piping |  | lf |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0
H-RI-MAN | H | 03 Rough-in (Labour) | Manifolds |  | ea |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0
H-RI-SUITE | H | 03 Rough-in (Labour) | Hydronic Insuite Piping |  | suite |  | 8 |  |  | Y | 0 | 0 | 0 | 0 | 0
H-RI-GLY | H | 03 Rough-in (Labour) | Glycol Loop |  | LS |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0
H-RI-CAN | H | 03 Rough-in (Labour) | Canning / Cutting / Layout |  | LS |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0
H-RI-CLN | H | 03 Rough-in (Labour) | Clean-up |  | LS |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0
H-FN-AP | H | 04 Finishing (Labour) | Install Access Panels |  | ea |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0
H-FN-LBL | H | 04 Finishing (Labour) | Pipe Labelling |  | LS |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0
H-EQ-MECH | H | 06 Fixtures & Equipment Supply | Mechanical Room |  | LS |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0
H-EQ-EQP | H | 06 Fixtures & Equipment Supply | Hydronic Equipment (boilers, pumps, HX) |  | LS |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0
H-TS-TEST | H | 07 Testing, TAB & Commissioning | Testing |  | LS |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
Note on C6: Phase the work happens in. Material on 03 Rough-in / 04 Finishing rows rolls into 05 Material Supply on BUDGET and SOV, the same way Knowify jobs are set up.
Note on E24: EXAMPLE quantity: 123 units from PRJ INFO, $800 ea and 12 hrs ea from the original 'Insuite Piping - $800 ea @ 12 HRS ea' label. Replace with your takeoff.
Note on I6: Lump material adjustment ($). Negative numbers allowed.
Note on J6: Lump hours adjustment. Negative numbers allowed.
Note on Q6: Labour actual / labour budget for this Div + Phase on the Knowify job pasted, using closed phases that used at least half their budget, and phases already at or over budget. A warning light, not a correction factor.

## HVAC EST
HVAC EST
Ventilation (V) and Air Conditioning (AC). Identical columns and formulas to PLUMBING EST.
TOTALS | [10 empty] | 0 | 0 | 0 | 0 | 0
Labour $ = Hours x crew-mix weighted burdened wage. Overhead $ = Hours x overhead $/hr. P/H rows use the P&H crew, V/AC rows use the HVAC crew. Q:R show how the same Div + Phase ran vs budget on the Knowify job pasted (1.30x = 30% over).
Item Code | Div | Phase | Description | Qty | Unit | Material $/Unit | Hrs/Unit | Add Material $ | Add Hrs | PST? (Y/N) | Material $ (incl PST) | Hours | Labour $ (wage+burden) | Overhead $ | TOTAL COST $ | Knowify Labour Actual/Budget | Knowify Material Actual/Budget | History Flag
V-RI-DUCT | V | 03 Rough-in (Labour) | Distribution Ductwork |  | lb |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0 | 1.7283 | 1.8919 | Past job ran over budget
V-RI-SUITE | V | 03 Rough-in (Labour) | Insuite Ductwork |  | suite |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0 | 1.7283 | 1.8919 | Past job ran over budget
V-RI-COND | V | 03 Rough-in (Labour) | Condensate Drains (if by HVAC) |  | LS |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0 | 1.7283 | 1.8919 | Past job ran over budget
V-RI-INS | V | 03 Rough-in (Labour) | Thermal Insulation (in-house) |  | LS |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0 | 1.7283 | 1.8919 | Past job ran over budget
V-RI-CAN | V | 03 Rough-in (Labour) | Canning / Cutting / Layout |  | LS |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0 | 1.7283 | 1.8919 | Past job ran over budget
V-RI-CLN | V | 03 Rough-in (Labour) | Clean-up |  | LS |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0 | 1.7283 | 1.8919 | Past job ran over budget
V-FN-GRL | V | 04 Finishing (Labour) | Grilles & Ventilation Terminations |  | ea |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0 | 0 | 1.8919 | Past job ran over budget
V-FN-AP | V | 04 Finishing (Labour) | Install Access Panels |  | ea |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0 | 0 | 1.8919 | Past job ran over budget
V-FN-LBL | V | 04 Finishing (Labour) | Duct Labelling |  | LS |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0 | 0 | 1.8919 | Past job ran over budget
V-EQ-FAN | V | 06 Fixtures & Equipment Supply | Ventilation Equipment Supply (fans, ERVs) |  | ea |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0
V-TS-TEST | V | 07 Testing, TAB & Commissioning | Testing |  | LS |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0
AC-RI-DUCT | AC | 03 Rough-in (Labour) | Distribution Ductwork |  | lb |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0
AC-RI-SUITE | AC | 03 Rough-in (Labour) | Insuite Ductwork |  | suite |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0
AC-RI-COND | AC | 03 Rough-in (Labour) | Condensate Drains (if by HVAC) |  | LS |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0
AC-RI-LINE | AC | 03 Rough-in (Labour) | Refrigeration Linesets |  | lf |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0
AC-RI-PTAC | AC | 03 Rough-in (Labour) | PTAC Rough-in |  | ea |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0
AC-RI-LS12 | AC | 03 Rough-in (Labour) | AC-1.1/2 Lineset |  | ea |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0
AC-RI-CAN | AC | 03 Rough-in (Labour) | Canning / Cutting / Layout |  | LS |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0
AC-RI-CLN | AC | 03 Rough-in (Labour) | Clean-up |  | LS |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0
AC-FN-GRL | AC | 04 Finishing (Labour) | Diffusers & Registers |  | ea |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0
AC-FN-AP | AC | 04 Finishing (Labour) | Install Access Panels |  | ea |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0
AC-EQ-AHU | AC | 06 Fixtures & Equipment Supply | AHUs & Heat Pumps Supply |  | ea |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0
AC-TS-TEST | AC | 07 Testing, TAB & Commissioning | Testing |  | LS |  |  |  |  | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
[10 empty] | Y | 0 | 0 | 0 | 0 | 0
Note on C6: Phase the work happens in. Material on 03 Rough-in / 04 Finishing rows rolls into 05 Material Supply on BUDGET and SOV, the same way Knowify jobs are set up.
Note on I6: Lump material adjustment ($). Negative numbers allowed.
Note on J6: Lump hours adjustment. Negative numbers allowed.
Note on Q6: Labour actual / labour budget for this Div + Phase on the Knowify job pasted, using closed phases that used at least half their budget, and phases already at or over budget. A warning light, not a correction factor.

## SUBS & GC
SUBTRADES & GENERAL CONDITIONS
Allocation %: enter a split per division, or leave all four blank to auto-split by direct cost.
[7 empty] | Direct cost by division | 233323.62 | 0 | 0 | 0
[7 empty] | Auto split share | 100% | 0% | 0% | 0%
SUBTRADES (each becomes its own SOV line, as in Knowify)
# | Item | Company / Basis | Phase | Qty | Unit | Rate $ | Amount $ | % P | % H | % V | % AC | Plumbing $ | Hydronic $ | Ventilation $ | A/C $ | Check
1 | Insulation and Heat Trace | Adler | 03 Rough-in (Labour) | 1 | LS |  | 0 | 100% |  |  |  | 0 | 0 | 0 | 0
2 | Duct Insulation |  | 03 Rough-in (Labour) | 1 | LS |  | 0 |  |  | 50% | 50% | 0 | 0 | 0 | 0
3 | Fire Sprinklers |  | 03 Rough-in (Labour) | 1 | LS |  | 0 | 100% |  |  |  | 0 | 0 | 0 | 0
4 | P&H Controls |  | 06 Fixtures & Equipment Supply | 1 | LS |  | 0 | 50% | 50% |  |  | 0 | 0 | 0 | 0
5 | HVAC Controls | Olympic Controls | 06 Fixtures & Equipment Supply | 1 | LS |  | 0 |  |  | 50% | 50% | 0 | 0 | 0 | 0
6 | TAB and Commissioning | Western Mechanical | 07 Testing, TAB & Commissioning | 1 | LS |  | 0 |  |  | 100% |  | 0 | 0 | 0 | 0
7 | A/C Commissioning |  | 07 Testing, TAB & Commissioning | 1 | LS |  | 0 |  |  |  | 100% | 0 | 0 | 0 | 0
8 | Canning / Piping Plans | Paris Mechanical | 01 Shop Drawings, Permits & Mobilization | 1 | LS |  | 0 | 100% |  |  |  | 0 | 0 | 0 | 0
9 | Coring / Scanning |  | 03 Rough-in (Labour) | 1 | LS |  | 0 |  |  |  |  | 0 | 0 | 0 | 0
10 | Fixtures Caulking | Paris Mechanical | 04 Finishing (Labour) | 1 | LS |  | 0 | 100% |  |  |  | 0 | 0 | 0 | 0
11 | Water Balancing | Western Mechanical | 07 Testing, TAB & Commissioning | 1 | LS |  | 0 | 100% |  |  |  | 0 | 0 | 0 | 0
12 | Sump Pumps |  | 06 Fixtures & Equipment Supply | 1 | LS |  | 0 | 100% |  |  |  | 0 | 0 | 0 | 0
13 | Chemical Treatment |  | 07 Testing, TAB & Commissioning | 1 | LS |  | 0 |  | 100% |  |  | 0 | 0 | 0 | 0
14 | P&H Seismic / Schedule |  | 03 Rough-in (Labour) | 1 | LS |  | 0 | 50% | 50% |  |  | 0 | 0 | 0 | 0
15 | HVAC Seismic / Schedule |  | 03 Rough-in (Labour) | 1 | LS |  | 0 |  |  | 50% | 50% | 0 | 0 | 0 | 0
16 | As-built Drawings | Paris Mechanical | 08 Completion & Final Documents | 1 | LS |  | 0 |  |  |  |  | 0 | 0 | 0 | 0
17 | O&M Manuals | Paris Mechanical | 08 Completion & Final Documents | 1 | LS |  | 0 |  |  |  |  | 0 | 0 | 0 | 0
18 | Plumbing Bond |  | 01 Shop Drawings, Permits & Mobilization | 1 | LS |  | 0 | 100% |  |  |  | 0 | 0 | 0 | 0
19 | HVAC Bond |  | 01 Shop Drawings, Permits & Mobilization | 1 | LS |  | 0 |  |  | 50% | 50% | 0 | 0 | 0 | 0
20 | Welding |  | 03 Rough-in (Labour) | 1 | LS |  | 0 |  |  | 100% |  | 0 | 0 | 0 | 0
21 | Gas Service / Other |  | 03 Rough-in (Labour) | 1 | LS |  | 0 |  |  |  |  | 0 | 0 | 0 | 0
22 |  |  |  | 1 | LS |  | 0 |  |  |  |  | 0 | 0 | 0 | 0
| SUBTRADES TOTAL | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0
GENERAL CONDITIONS (Qty x Rate)
# | Item | Company / Basis | Phase | Qty | Unit | Rate $ | Amount $ | % P | % H | % V | % AC | Plumbing $ | Hydronic $ | Ventilation $ | A/C $ | Check
1 | Supervision - Plumbing |  | 09 Office, Supervision & General | 24 | months |  | 0 | 100% |  |  |  | 0 | 0 | 0 | 0
2 | Supervision - Hydronic |  | 09 Office, Supervision & General | 24 | months |  | 0 |  | 100% |  |  | 0 | 0 | 0 | 0
3 | Supervision - Ventilation |  | 09 Office, Supervision & General | 24 | months |  | 0 |  |  | 100% |  | 0 | 0 | 0 | 0
4 | Supervision - A/C |  | 09 Office, Supervision & General | 24 | months |  | 0 |  |  |  | 100% | 0 | 0 | 0 | 0
5 | Office Project Manager (dedicated to this job) | Dedicated office PM, per month | 09 Office, Supervision & General | 24 | months | 7500 | 180000 |  |  |  |  | 180000 | 0 | 0 | 0 | OK
6 | Health & Safety |  | 09 Office, Supervision & General | 24 | months |  | 0 |  |  |  |  | 0 | 0 | 0 | 0
7 | Bonus - Plumbing |  | 09 Office, Supervision & General | 1 | LS |  | 0 | 100% |  |  |  | 0 | 0 | 0 | 0
8 | Bonus - Hydronic |  | 09 Office, Supervision & General | 1 | LS |  | 0 |  | 100% |  |  | 0 | 0 | 0 | 0
9 | Bonus - Ventilation |  | 09 Office, Supervision & General | 1 | LS |  | 0 |  |  | 100% |  | 0 | 0 | 0 | 0
10 | Bonus - A/C |  | 09 Office, Supervision & General | 1 | LS |  | 0 |  |  |  | 100% | 0 | 0 | 0 | 0
11 | Bonus - Office |  | 09 Office, Supervision & General | 1 | LS |  | 0 |  |  |  |  | 0 | 0 | 0 | 0
12 | Shop Drawings |  | 01 Shop Drawings, Permits & Mobilization | 1 | LS |  | 0 |  |  |  |  | 0 | 0 | 0 | 0
13 | Plumbing & Gas Permit |  | 01 Shop Drawings, Permits & Mobilization | 1 | LS |  | 0 | 100% |  |  |  | 0 | 0 | 0 | 0
14 | Prints |  | 01 Shop Drawings, Permits & Mobilization | 1 | LS |  | 0 |  |  |  |  | 0 | 0 | 0 | 0
15 | Rentals |  | 09 Office, Supervision & General | 4 | months |  | 0 |  |  |  |  | 0 | 0 | 0 | 0
16 | Trailer |  | 09 Office, Supervision & General | 12 | months |  | 0 |  |  |  |  | 0 | 0 | 0 | 0
17 | Legal Fees |  | 09 Office, Supervision & General | 24 | months |  | 0 |  |  |  |  | 0 | 0 | 0 | 0
18 | Freight |  | 09 Office, Supervision & General | 24 | months |  | 0 |  |  |  |  | 0 | 0 | 0 | 0
19 | Warranty Reserve - Plumbing |  | 08 Completion & Final Documents | 1 | LS | 0 | 0 | 100% |  |  |  | 0 | 0 | 0 | 0
20 | Warranty Reserve - Hydronic |  | 08 Completion & Final Documents | 1 | LS | 0 | 0 |  | 100% |  |  | 0 | 0 | 0 | 0
21 | Warranty Reserve - Ventilation |  | 08 Completion & Final Documents | 1 | LS | 0 | 0 |  |  | 100% |  | 0 | 0 | 0 | 0
22 | Warranty Reserve - Air Conditioning |  | 08 Completion & Final Documents | 1 | LS | 0 | 0 |  |  |  | 100% | 0 | 0 | 0 | 0
23 | [6 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0
24 | [6 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0
25 | [6 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0
26 | [6 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0
27 | [6 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0
28 | [6 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0
| GENERAL CONDITIONS TOTAL | [5 empty] | 180000 |  |  |  |  | 180000 | 0 | 0 | 0
Note on B33: Confirmed: field supervision here is separate from the Foreman & PM share of the crew mix.
Note on B38: Knowify charges the Health & Safety Coordinator's time to the job (237 hrs on 405 Marie Place).
Note on G37: $7,500/month from original PRJ INFO D53. Confirmed: the $22/hr overhead covers salaried staff company wide; this is the PM assigned to this job, so it is not a double count. Auto-splits by direct cost across divisions.

## BID SUMMARY
BID SUMMARY: full cost, then margin
(enter project name on INPUTS) ¦ 2650 East 41st Ave, Vancouver | [9 empty] | Bid status: | OK
Code | Division | Hours | Labour $ (wage+burden) | Overhead $ | Material $ (incl PST) | Consumables $ | Subtrades $ | Gen. Cond. $ | Contingency $ | TOTAL COST $ | Target Margin | Sell Price $ | CONTRACT $ (rounded) | Gross Profit $ | Actual Margin | Markup on Cost | Per Unit $ | Per Sq Ft $ | Hrs / Unit
P | Plumbing | 1476 | 95563.62 | 32472 | 105288 | 2105.76 | 0 | 180000 | 0 | 415429.38 | 15% | 488740.4471 | 488800 | 73370.62 | 15.01% | 17.66% | 3973.9837 | 0 | 12
H | Hydronic | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0
V | Ventilation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0
AC | Air Conditioning | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0
| TOTAL MECHANICAL | 1476 | 95563.62 | 32472 | 105288 | 2105.76 | 0 | 180000 | 0 | 415429.38 |  | 488740.4471 | 488800 | 73370.62 | 15.01% | 17.66% | 3973.9837 | 0 | 12
[12 empty] | GST (not in contract cost) | 24440
[12 empty] | Contract + GST | 513240
COST OF GOODS MIX (whole job)
| Cost Type |  | This Bid $ | % of Contract | % of Total Cost | Knowify Job % of Cost | Your Typical % of Cost | Bid vs Typical
| Labour (wage + burden) |  | 95563.62 | 19.55% | 23% | 29.39% |  |  |  | Knowify job % uses projected cost (larger of budget or actual, per phase).
| Overhead |  | 32472 | 6.643% | 7.816% | not tracked |  |  |  | Knowify does not carry company overhead; its office and safety time sits in labour.
| Material: pipe, fittings, valves (+PST, consumables) |  | 107393.76 | 21.97% | 25.85% | 25.88% | 26% | -0.1487% |  | Knowify 'General Conditions' = its Equipment cost type (tools, rentals).
| Fixtures & Equipment Supply |  | 0 | 0% | 0% | 20.38%
| Subtrades |  | 0 | 0% | 0% | 24.33%
| General Conditions |  | 180000 | 36.82% | 43.33% | 0.02391%
| Contingency |  | 0 | 0% | 0%
| Gross Profit |  | 73370.62 | 15.01%
| TOTAL |  | 488800 | 100% | 100%
CHECKS (all must read OK before the bid goes out)
| P&H crew mix = 100% and labour ties to wage breakdown | [6 empty] | OK
| HVAC crew mix = 100% and labour ties to wage breakdown | [6 empty] | OK
| P+H labour $ = LABOUR RATES P&H cost by wage breakdown | [6 empty] | OK
| V+AC labour $ = LABOUR RATES HVAC cost by wage breakdown | [6 empty] | OK
| Every estimate row has a valid Div and Phase | [6 empty] | OK
| Subtrades fully allocated to divisions | [6 empty] | OK
| General conditions fully allocated to divisions | [6 empty] | OK
| Level weights total 100% | [6 empty] | OK
| BUDGET total cost = BID SUMMARY total cost (every sub/GC row has a phase) | [6 empty] | OK
| SCHEDULE OF VALUES total = contract | [6 empty] | OK
| OVERALL | [6 empty] | OK

## BUDGET
PROJECT BUDGET (cost, by division and phase)
Quote:
PROJECT ROLL-UP
| Division | Hours | Labour $ | Overhead $ | Material $ (incl consumables) | Subtrades $ | Gen. Cond. $ | Contingency $ | TOTAL COST $ | Margin $ | CONTRACT $
| Plumbing | 1476 | 95563.62 | 32472 | 107393.76 | 0 | 180000 | 0 | 415429.38 | 73370.62 | 488800
| Hydronic | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ventilation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Air Conditioning | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL | 1476 | 95563.62 | 32472 | 107393.76 | 0 | 180000 | 0 | 415429.38 | 73370.62 | 488800
| Total cost rebuilt from phase detail below (must equal J10) | [7 empty] | 415429.38 | OK
Material on 03 Rough-in and 04 Finishing rows is shown under 05 Material Supply (Knowify setup).
PLUMBING (P)
| Phase | Hours | Labour $ | Overhead $ | Material $ | Subtrades $ | Gen. Cond. $ |  | TOTAL BUDGET $ | % of Division
| 01 Shop Drawings, Permits & Mobilization | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
| 02 Foundation & Underground | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
| 03 Rough-in (Labour) | 1476 | 95563.62 | 32472 | 0 | 0 | 0 |  | 128035.62 | 30.82%
| 04 Finishing (Labour) | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
| 05 Material Supply | 0 | 0 | 0 | 105288 | 0 | 0 |  | 105288 | 25.34%
| 06 Fixtures & Equipment Supply | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
| 07 Testing, TAB & Commissioning | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
| 08 Completion & Final Documents | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
| 09 Office, Supervision & General | 0 | 0 | 0 | 0 | 0 | 180000 |  | 180000 | 43.33%
| Consumables allowance |  |  |  | 2105.76 |  |  |  | 2105.76 | 0.5069%
| Contingency | [7 empty] | 0 | 0%
| TOTAL COST BUDGET | 1476 | 95563.62 | 32472 | 107393.76 | 0 | 180000 |  | 415429.38
| Margin (fee) | [7 empty] | 73370.62
| CONTRACT VALUE | [7 empty] | 488800
HYDRONIC (H)
| Phase | Hours | Labour $ | Overhead $ | Material $ | Subtrades $ | Gen. Cond. $ |  | TOTAL BUDGET $ | % of Division
| 01 Shop Drawings, Permits & Mobilization | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
| 02 Foundation & Underground | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
| 03 Rough-in (Labour) | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
| 04 Finishing (Labour) | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
| 05 Material Supply | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
| 06 Fixtures & Equipment Supply | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
| 07 Testing, TAB & Commissioning | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
| 08 Completion & Final Documents | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
| 09 Office, Supervision & General | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
| Consumables allowance |  |  |  | 0 |  |  |  | 0 | 0%
| Contingency | [7 empty] | 0 | 0%
| TOTAL COST BUDGET | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| Margin (fee) | [7 empty] | 0
| CONTRACT VALUE | [7 empty] | 0
VENTILATION (V)
| Phase | Hours | Labour $ | Overhead $ | Material $ | Subtrades $ | Gen. Cond. $ |  | TOTAL BUDGET $ | % of Division
| 01 Shop Drawings, Permits & Mobilization | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
| 02 Foundation & Underground | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
| 03 Rough-in (Labour) | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
| 04 Finishing (Labour) | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
| 05 Material Supply | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
| 06 Fixtures & Equipment Supply | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
| 07 Testing, TAB & Commissioning | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
| 08 Completion & Final Documents | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
| 09 Office, Supervision & General | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
| Consumables allowance |  |  |  | 0 |  |  |  | 0 | 0%
| Contingency | [7 empty] | 0 | 0%
| TOTAL COST BUDGET | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| Margin (fee) | [7 empty] | 0
| CONTRACT VALUE | [7 empty] | 0
AIR CONDITIONING (AC)
| Phase | Hours | Labour $ | Overhead $ | Material $ | Subtrades $ | Gen. Cond. $ |  | TOTAL BUDGET $ | % of Division
| 01 Shop Drawings, Permits & Mobilization | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
| 02 Foundation & Underground | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
| 03 Rough-in (Labour) | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
| 04 Finishing (Labour) | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
| 05 Material Supply | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
| 06 Fixtures & Equipment Supply | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
| 07 Testing, TAB & Commissioning | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
| 08 Completion & Final Documents | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
| 09 Office, Supervision & General | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0%
| Consumables allowance |  |  |  | 0 |  |  |  | 0 | 0%
| Contingency | [7 empty] | 0 | 0%
| TOTAL COST BUDGET | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| Margin (fee) | [7 empty] | 0
| CONTRACT VALUE | [7 empty] | 0

## SCHEDULE OF VALUES
SCHEDULE OF VALUES
2650 East 41st Ave, Vancouver GC:
| Contract value (from BID SUMMARY) | 488800
| Total of schedule below | 488800 | OK
Line names follow your Knowify setup. Columns J:N are the cost budget for the same line, ready to load into Knowify.
KNOWIFY COST BUDGET (no overhead, no margin)
Item # | Job Phase / Contract Item | Scheduled Value $ | % of Contract | Completed to Date $ | % Complete | Balance to Finish $ | Holdback $ | Material $ | Labour $ | Subtrades $ | Other $ | Hours | Div factor
P | PLUMBING | 488800 | 100% | 0 |  | 488800 | 0 | 107393.76 | 95563.62 | 0 | 180000 | 1476 | 1.1826
P-01 | P - Shop Drawings, Permits & Mobilization | 0 | 0% |  | 0% | 0 | 0 | 0 | 0 |  | 0 | 0
P-02 | P - Foundation & Underground | 0 | 0% |  | 0% | 0 | 0 | 0 | 0 |  | 0 | 0
P-03-01 | P - U/G Plumbing Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-03-02 | P - P-02 Plumbing Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-03-03 | P - PRKG Plumbing Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-03-04 | P - L-01 Plumbing Rough-in (Labour) | 29544.5862 | 6.044% |  | 0% | 29544.5862 | 0 |  | 18646.56 |  | 0 | 288
P-03-05 | P - L-02 Plumbing Rough-in (Labour) | 30775.6106 | 6.296% |  | 0% | 30775.6106 | 0 |  | 19423.5 |  | 0 | 300
P-03-06 | P - L-03 Plumbing Rough-in (Labour) | 30775.6106 | 6.296% |  | 0% | 30775.6106 | 0 |  | 19423.5 |  | 0 | 300
P-03-07 | P - L-04 Plumbing Rough-in (Labour) | 30775.6106 | 6.296% |  | 0% | 30775.6106 | 0 |  | 19423.5 |  | 0 | 300
P-03-08 | P - L-05 Plumbing Rough-in (Labour) | 29544.5862 | 6.044% |  | 0% | 29544.5862 | 0 |  | 18646.56 |  | 0 | 288
P-03-09 | P - L-06 Plumbing Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-03-10 | P - L-07 Plumbing Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-03-11 | P - L-08 Plumbing Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-03-12 | P - L-09 Plumbing Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-03-13 | P - L-10 Plumbing Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-03-14 | P - ROOF Plumbing Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-03-15 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-03-16 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-03-17 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-03-18 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-03-19 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-03-20 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-03-21 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-03-22 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-03-23 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-03-24 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-04-01 | P - U/G Plumbing Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-04-02 | P - P-02 Plumbing Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-04-03 | P - PRKG Plumbing Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-04-04 | P - L-01 Plumbing Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-04-05 | P - L-02 Plumbing Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-04-06 | P - L-03 Plumbing Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-04-07 | P - L-04 Plumbing Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-04-08 | P - L-05 Plumbing Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-04-09 | P - L-06 Plumbing Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-04-10 | P - L-07 Plumbing Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-04-11 | P - L-08 Plumbing Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-04-12 | P - L-09 Plumbing Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-04-13 | P - L-10 Plumbing Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-04-14 | P - ROOF Plumbing Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-04-15 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-04-16 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-04-17 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-04-18 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-04-19 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-04-20 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-04-21 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-04-22 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-04-23 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-04-24 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
P-05 | P - Material Supply | 124514.4771 | 25.47% |  | 0% | 124514.4771 | 0 | 107393.76 | 0 |  | 0 | 0
P-06 | P - Fixtures & Equipment Supply | 0 | 0% |  | 0% | 0 | 0 | 0 | 0 |  | 0 | 0
P-07 | P - Testing, TAB & Commissioning | 0 | 0% |  | 0% | 0 | 0 | 0 | 0 |  | 0 | 0
P-08 | P - Completion & Final Documents | 0 | 0% |  | 0% | 0 | 0 | 0 | 0 |  | 0 | 0
P-09 | P - Office, Supervision & General | 212869.5186 | 43.55% |  | 0% | 212869.5186 | 0 | 0 | 0 |  | 180000 | 0
P-S01 | P - Insulation and Heat Trace | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
P-S02 | P - Duct Insulation | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
P-S03 | P - Fire Sprinklers | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
P-S04 | P - P&H Controls | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
P-S05 | P - HVAC Controls | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
P-S06 | P - TAB and Commissioning | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
P-S07 | P - A/C Commissioning | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
P-S08 | P - Canning / Piping Plans | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
P-S09 | P - Coring / Scanning | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
P-S10 | P - Fixtures Caulking | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
P-S11 | P - Water Balancing | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
P-S12 | P - Sump Pumps | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
P-S13 | P - Chemical Treatment | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
P-S14 | P - P&H Seismic / Schedule | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
P-S15 | P - HVAC Seismic / Schedule | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
P-S16 | P - As-built Drawings | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
P-S17 | P - O&M Manuals | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
P-S18 | P - Plumbing Bond | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
P-S19 | P - HVAC Bond | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
P-S20 | P - Welding | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
P-S21 | P - Gas Service / Other | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
P-S22 |  | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
H | HYDRONIC | 0 | 0% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
H-01 | H - Shop Drawings, Permits & Mobilization | 0 | 0% |  | 0% | 0 | 0 | 0 | 0 |  | 0 | 0
H-02 | H - Foundation & Underground | 0 | 0% |  | 0% | 0 | 0 | 0 | 0 |  | 0 | 0
H-03-01 | H - U/G Hydronic Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-03-02 | H - P-02 Hydronic Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-03-03 | H - PRKG Hydronic Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-03-04 | H - L-01 Hydronic Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-03-05 | H - L-02 Hydronic Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-03-06 | H - L-03 Hydronic Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-03-07 | H - L-04 Hydronic Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-03-08 | H - L-05 Hydronic Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-03-09 | H - L-06 Hydronic Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-03-10 | H - L-07 Hydronic Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-03-11 | H - L-08 Hydronic Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-03-12 | H - L-09 Hydronic Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-03-13 | H - L-10 Hydronic Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-03-14 | H - ROOF Hydronic Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-03-15 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-03-16 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-03-17 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-03-18 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-03-19 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-03-20 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-03-21 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-03-22 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-03-23 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-03-24 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-04-01 | H - U/G Hydronic Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-04-02 | H - P-02 Hydronic Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-04-03 | H - PRKG Hydronic Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-04-04 | H - L-01 Hydronic Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-04-05 | H - L-02 Hydronic Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-04-06 | H - L-03 Hydronic Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-04-07 | H - L-04 Hydronic Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-04-08 | H - L-05 Hydronic Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-04-09 | H - L-06 Hydronic Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-04-10 | H - L-07 Hydronic Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-04-11 | H - L-08 Hydronic Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-04-12 | H - L-09 Hydronic Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-04-13 | H - L-10 Hydronic Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-04-14 | H - ROOF Hydronic Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-04-15 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-04-16 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-04-17 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-04-18 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-04-19 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-04-20 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-04-21 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-04-22 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-04-23 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-04-24 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
H-05 | H - Material Supply | 0 | 0% |  | 0% | 0 | 0 | 0 | 0 |  | 0 | 0
H-06 | H - Fixtures & Equipment Supply | 0 | 0% |  | 0% | 0 | 0 | 0 | 0 |  | 0 | 0
H-07 | H - Testing, TAB & Commissioning | 0 | 0% |  | 0% | 0 | 0 | 0 | 0 |  | 0 | 0
H-08 | H - Completion & Final Documents | 0 | 0% |  | 0% | 0 | 0 | 0 | 0 |  | 0 | 0
H-09 | H - Office, Supervision & General | 0 | 0% |  | 0% | 0 | 0 | 0 | 0 |  | 0 | 0
H-S01 | H - Insulation and Heat Trace | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
H-S02 | H - Duct Insulation | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
H-S03 | H - Fire Sprinklers | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
H-S04 | H - P&H Controls | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
H-S05 | H - HVAC Controls | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
H-S06 | H - TAB and Commissioning | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
H-S07 | H - A/C Commissioning | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
H-S08 | H - Canning / Piping Plans | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
H-S09 | H - Coring / Scanning | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
H-S10 | H - Fixtures Caulking | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
H-S11 | H - Water Balancing | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
H-S12 | H - Sump Pumps | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
H-S13 | H - Chemical Treatment | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
H-S14 | H - P&H Seismic / Schedule | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
H-S15 | H - HVAC Seismic / Schedule | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
H-S16 | H - As-built Drawings | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
H-S17 | H - O&M Manuals | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
H-S18 | H - Plumbing Bond | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
H-S19 | H - HVAC Bond | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
H-S20 | H - Welding | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
H-S21 | H - Gas Service / Other | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
H-S22 |  | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
V | VENTILATION | 0 | 0% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
V-01 | V - Shop Drawings, Permits & Mobilization | 0 | 0% |  | 0% | 0 | 0 | 0 | 0 |  | 0 | 0
V-02 | V - Foundation & Underground | 0 | 0% |  | 0% | 0 | 0 | 0 | 0 |  | 0 | 0
V-03-01 | V - U/G Ventilation Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-03-02 | V - P-02 Ventilation Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-03-03 | V - PRKG Ventilation Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-03-04 | V - L-01 Ventilation Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-03-05 | V - L-02 Ventilation Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-03-06 | V - L-03 Ventilation Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-03-07 | V - L-04 Ventilation Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-03-08 | V - L-05 Ventilation Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-03-09 | V - L-06 Ventilation Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-03-10 | V - L-07 Ventilation Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-03-11 | V - L-08 Ventilation Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-03-12 | V - L-09 Ventilation Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-03-13 | V - L-10 Ventilation Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-03-14 | V - ROOF Ventilation Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-03-15 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-03-16 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-03-17 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-03-18 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-03-19 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-03-20 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-03-21 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-03-22 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-03-23 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-03-24 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-04-01 | V - U/G Ventilation Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-04-02 | V - P-02 Ventilation Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-04-03 | V - PRKG Ventilation Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-04-04 | V - L-01 Ventilation Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-04-05 | V - L-02 Ventilation Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-04-06 | V - L-03 Ventilation Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-04-07 | V - L-04 Ventilation Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-04-08 | V - L-05 Ventilation Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-04-09 | V - L-06 Ventilation Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-04-10 | V - L-07 Ventilation Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-04-11 | V - L-08 Ventilation Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-04-12 | V - L-09 Ventilation Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-04-13 | V - L-10 Ventilation Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-04-14 | V - ROOF Ventilation Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-04-15 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-04-16 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-04-17 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-04-18 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-04-19 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-04-20 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-04-21 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-04-22 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-04-23 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-04-24 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
V-05 | V - Material Supply | 0 | 0% |  | 0% | 0 | 0 | 0 | 0 |  | 0 | 0
V-06 | V - Fixtures & Equipment Supply | 0 | 0% |  | 0% | 0 | 0 | 0 | 0 |  | 0 | 0
V-07 | V - Testing, TAB & Commissioning | 0 | 0% |  | 0% | 0 | 0 | 0 | 0 |  | 0 | 0
V-08 | V - Completion & Final Documents | 0 | 0% |  | 0% | 0 | 0 | 0 | 0 |  | 0 | 0
V-09 | V - Office, Supervision & General | 0 | 0% |  | 0% | 0 | 0 | 0 | 0 |  | 0 | 0
V-S01 | V - Insulation and Heat Trace | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
V-S02 | V - Duct Insulation | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
V-S03 | V - Fire Sprinklers | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
V-S04 | V - P&H Controls | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
V-S05 | V - HVAC Controls | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
V-S06 | V - TAB and Commissioning | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
V-S07 | V - A/C Commissioning | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
V-S08 | V - Canning / Piping Plans | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
V-S09 | V - Coring / Scanning | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
V-S10 | V - Fixtures Caulking | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
V-S11 | V - Water Balancing | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
V-S12 | V - Sump Pumps | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
V-S13 | V - Chemical Treatment | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
V-S14 | V - P&H Seismic / Schedule | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
V-S15 | V - HVAC Seismic / Schedule | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
V-S16 | V - As-built Drawings | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
V-S17 | V - O&M Manuals | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
V-S18 | V - Plumbing Bond | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
V-S19 | V - HVAC Bond | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
V-S20 | V - Welding | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
V-S21 | V - Gas Service / Other | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
V-S22 |  | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
AC | AIR CONDITIONING | 0 | 0% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AC-01 | AC - Shop Drawings, Permits & Mobilization | 0 | 0% |  | 0% | 0 | 0 | 0 | 0 |  | 0 | 0
AC-02 | AC - Foundation & Underground | 0 | 0% |  | 0% | 0 | 0 | 0 | 0 |  | 0 | 0
AC-03-01 | AC - U/G Air Conditioning Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-03-02 | AC - P-02 Air Conditioning Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-03-03 | AC - PRKG Air Conditioning Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-03-04 | AC - L-01 Air Conditioning Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-03-05 | AC - L-02 Air Conditioning Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-03-06 | AC - L-03 Air Conditioning Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-03-07 | AC - L-04 Air Conditioning Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-03-08 | AC - L-05 Air Conditioning Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-03-09 | AC - L-06 Air Conditioning Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-03-10 | AC - L-07 Air Conditioning Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-03-11 | AC - L-08 Air Conditioning Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-03-12 | AC - L-09 Air Conditioning Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-03-13 | AC - L-10 Air Conditioning Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-03-14 | AC - ROOF Air Conditioning Rough-in (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-03-15 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-03-16 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-03-17 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-03-18 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-03-19 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-03-20 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-03-21 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-03-22 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-03-23 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-03-24 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-04-01 | AC - U/G Air Conditioning Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-04-02 | AC - P-02 Air Conditioning Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-04-03 | AC - PRKG Air Conditioning Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-04-04 | AC - L-01 Air Conditioning Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-04-05 | AC - L-02 Air Conditioning Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-04-06 | AC - L-03 Air Conditioning Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-04-07 | AC - L-04 Air Conditioning Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-04-08 | AC - L-05 Air Conditioning Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-04-09 | AC - L-06 Air Conditioning Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-04-10 | AC - L-07 Air Conditioning Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-04-11 | AC - L-08 Air Conditioning Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-04-12 | AC - L-09 Air Conditioning Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-04-13 | AC - L-10 Air Conditioning Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-04-14 | AC - ROOF Air Conditioning Finishing (Labour) | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-04-15 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-04-16 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-04-17 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-04-18 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-04-19 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-04-20 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-04-21 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-04-22 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-04-23 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-04-24 |  | 0 | 0% |  | 0% | 0 | 0 |  | 0 |  | 0 | 0
AC-05 | AC - Material Supply | 0 | 0% |  | 0% | 0 | 0 | 0 | 0 |  | 0 | 0
AC-06 | AC - Fixtures & Equipment Supply | 0 | 0% |  | 0% | 0 | 0 | 0 | 0 |  | 0 | 0
AC-07 | AC - Testing, TAB & Commissioning | 0 | 0% |  | 0% | 0 | 0 | 0 | 0 |  | 0 | 0
AC-08 | AC - Completion & Final Documents | 0 | 0% |  | 0% | 0 | 0 | 0 | 0 |  | 0 | 0
AC-09 | AC - Office, Supervision & General | 0 | 0% |  | 0% | 0 | 0 | 0 | 0 |  | 0 | 0
AC-S01 | AC - Insulation and Heat Trace | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
AC-S02 | AC - Duct Insulation | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
AC-S03 | AC - Fire Sprinklers | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
AC-S04 | AC - P&H Controls | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
AC-S05 | AC - HVAC Controls | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
AC-S06 | AC - TAB and Commissioning | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
AC-S07 | AC - A/C Commissioning | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
AC-S08 | AC - Canning / Piping Plans | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
AC-S09 | AC - Coring / Scanning | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
AC-S10 | AC - Fixtures Caulking | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
AC-S11 | AC - Water Balancing | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
AC-S12 | AC - Sump Pumps | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
AC-S13 | AC - Chemical Treatment | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
AC-S14 | AC - P&H Seismic / Schedule | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
AC-S15 | AC - HVAC Seismic / Schedule | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
AC-S16 | AC - As-built Drawings | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
AC-S17 | AC - O&M Manuals | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
AC-S18 | AC - Plumbing Bond | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
AC-S19 | AC - HVAC Bond | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
AC-S20 | AC - Welding | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
AC-S21 | AC - Gas Service / Other | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
AC-S22 |  | 0 | 0% |  | 0% | 0 | 0 |  |  | 0
| TOTAL CONTRACT | 488800 | 100% | 0 | 0% | 488800 | 0 | 107393.76 | 95563.62 | 0 | 180000 | 1476
| Check: Knowify budget + overhead + contingency + margin = contract | [6 empty] | 488800 | OK
Note on P9: Contract for this division / its total phase cost. Spreads margin, consumables and contingency evenly.
Note on P88: Contract for this division / its total phase cost. Spreads margin, consumables and contingency evenly.
Note on P167: Contract for this division / its total phase cost. Spreads margin, consumables and contingency evenly.
Note on P246: Contract for this division / its total phase cost. Spreads margin, consumables and contingency evenly.

## KNOWIFY REVIEW
KNOWIFY REVIEW: what the last job actually cost
Reads KNOWIFY PHASES and KNOWIFY TIME. Blue cells: type from the export's Summary sheet. | [9 empty] | HELPER COLUMNS (one row per KNOWIFY PHASES row; do not edit) | [17 empty] | Role | Hours | Cost | Crew Class
[10 empty] | Knowify Phase | Div | Mapped Phase | Use | Lab Bud | Lab Act | Mat Bud | Mat Act | Sub Bud | Sub Act | Eq Bud | Eq Act | Tot Bud | Tot Act | Proj Lab | Proj Mat | Proj Sub | Proj Eq | Apprentice Lvl 3 | 24 | 1325.04 | Apprentice Lvl 3-6 | PHASE KEYWORD MAP (last match wins) |  | ROLE MAP (Knowify role -> crew class)
| Job | 0-MARC25102 - 405 Marie Place (Ashton) | [7 empty] | Fire Sprinklers | Other | 03 Rough-in (Labour) | 0 | 0 | 0 | 0 | 0 | 940000 | 833305.74 | 0 | 0 | 940000 | 833305.74 | 0 | 0 | 940000 | 0 | Foreman Lvl 2 | 43 | 3550.5 | Foreman & PM | Keyword in Knowify phase | Maps to Phase | Knowify Role (exact) | Crew Class
| Contract (Knowify 'Total Amount') | 9663139.81 | [7 empty] | P - Water Connection Temporary | P | 01 Shop Drawings, Permits & Mobilization | 1 | 4000 | 530.01 | 1500 | 3203.97 | 0 | 0 | 0 | 0 | 5500 | 3733.98 | 4000 | 3203.97 | 0 | 0 | Apprentice Lvl 1 | 837.6667 | 40180.24 | Apprentice Lvl 1-2 | Water Connection | 01 Shop Drawings, Permits & Mobilization | Apprentice Lvl 1 | Apprentice Lvl 1-2
| Committed cost (Knowify 'Total Cost To Date (Committed)') | 8998706.78 | [7 empty] | P - Foundation Plumbing & Sumps | P | 02 Foundation & Underground | 1 | 35000 | 60524.63 | 125000 | 127755.62 | 0 | 0 | 0 | 0 | 160000 | 188280.25 | 60524.63 | 127755.62 | 0 | 0 | Foreman Lvl 2 | 1221.8333 | 81644.43 | Foreman & PM | Shop Drawing | 01 Shop Drawings, Permits & Mobilization | Apprentice Lvl 2 | Apprentice Lvl 1-2
[10 empty] | P - Parkade Plumbing (Labour & Material) | P | 03 Rough-in (Labour) | 0 | 70000 | 109892.33 | 110000 | 60999.27 | 0 | 0 | 0 | 1383.76 | 180000 | 172275.36 | 109892.33 | 110000 | 0 | 1383.76 | Apprentice Lvl 1 | 3 | 82.74 | Apprentice Lvl 1-2 | Permit | 01 Shop Drawings, Permits & Mobilization | Apprentice Lvl 3 | Apprentice Lvl 3-6
| HEADLINE | [8 empty] | P - BLDG A - L1 Plumbing Rough-in (Labour) | P | 03 Rough-in (Labour) | 1 | 40000 | 78969.73 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 78969.73 | 78969.73 | 0 | 0 | 0 | Apprentice Lvl 1 | 993.6667 | 37200.9 | Apprentice Lvl 1-2 | Mobilization | 01 Shop Drawings, Permits & Mobilization | Apprentice Lvl 4 | Apprentice Lvl 3-6
| Measure | Amount | Margin % | Cost Mix (projected) | Amount | % of Cost |  |  |  | P - BLDG A - L2 Plumbing Rough-in (Labour) | P | 03 Rough-in (Labour) | 1 | 40000 | 44124.47 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 44124.47 | 44124.47 | 0 | 0 | 0 | Apprentice Lvl 1 | 532.5833 | 26480 | Apprentice Lvl 1-2 | Foundation | 02 Foundation & Underground | Apprentice Lvl 5 | Apprentice Lvl 3-6
| Knowify cost budget | 8232377.54 | 14.81% | Material excl. fixtures & equip. supply | 2361476.17 | 25.88% |  |  |  | P - BLDG A - L3 Plumbing Rough-in (Labour) | P | 03 Rough-in (Labour) | 1 | 40000 | 37888.74 | 0 | 0 | 0 | 4331.25 | 0 | 0 | 40000 | 42219.99 | 40000 | 0 | 4331.25 | 0 | Apprentice Lvl 3 | 712.5 | 37728.33 | Apprentice Lvl 3-6 | Underground | 02 Foundation & Underground | Apprentice Lvl 6 | Apprentice Lvl 3-6
| Cost to date (actual) | 6004615.96 |  | Your typical pipe/fitting material % |  | 26% |  |  |  | P - BLDG A - L4 Plumbing Rough-in (Labour) | P | 03 Rough-in (Labour) | 1 | 40000 | 43632.52 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 43632.52 | 43632.52 | 0 | 0 | 0 | Journeyman Lvl 2 | 530.5 | 38320.57 | Journeyman Lvl 1-2 | U/G | 02 Foundation & Underground | Apprentice Level 6 | Apprentice Lvl 3-6
| Projected cost (larger of budget or actual, per phase) | 9126402.75 | 5.554% | Fixtures & equipment supply | 1860000 | 20.38% |  |  |  | P - BLDG A - L5 Plumbing Rough-in (Labour) | P | 03 Rough-in (Labour) | 1 | 40000 | 38544.91 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 38544.91 | 40000 | 0 | 0 | 0 | Journeyman Lvl 2 | 1586.0833 | 88613.26 | Journeyman Lvl 1-2 | Parkade | 03 Rough-in (Labour) | Apprentice Lvl 7 | Apprentice Lvl 7-8
| Committed cost (typed above) | 8998706.78 | 6.876% | [6 empty] | P - BLDG A - L6 Plumbing Rough-in (Labour) | P | 03 Rough-in (Labour) | 1 | 40000 | 29711.57 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 29711.57 | 40000 | 0 | 0 | 0 | Apprentice Lvl 1 | 817.0833 | 40619.1 | Apprentice Lvl 1-2 | Rough-in | 03 Rough-in (Labour) | Apprentice Lvl 8 | Apprentice Lvl 7-8
| Labour hours to date (KNOWIFY TIME) | 32620.9167 |  | Labour | 2682310.2 | 29.39% |  |  |  | P - BLDG A - Roof Plumbing (Labour & Material) | P | 03 Rough-in (Labour) | 0 | 27600 | 491.54 | 12400 | 0 | 0 | 0 | 0 | 0 | 40000 | 491.54 | 27600 | 12400 | 0 | 0 | Apprentice Lvl 1 | 23.75 | 654.87 | Apprentice Lvl 1-2 | Roof | 03 Rough-in (Labour) | Journeyman | Journeyman Lvl 1-2
| Company overhead on those hours (not in Knowify) | 717660.1667 |  | Material | 4221476.17 | 46.26% |  |  |  | P - BLDG A - Material Supply | P | 05 Material Supply | 1 | 0 | 0 | 200000 | 263945.54 | 0 | 0 | 0 | 38.39 | 200000 | 263983.93 | 0 | 263945.54 | 0 | 38.39 | Apprentice Lvl 2 | 1276 | 48723.69 | Apprentice Lvl 1-2 | Insulation | 03 Rough-in (Labour) | Journeyman Lvl 1 | Journeyman Lvl 1-2
| Margin at projected cost, after overhead |  | -1.872% | Subtrades | 2220434.25 | 24.33% |  |  |  | P - BLDG A - Plumbing Fixtures & Access Panels Supply | P | 06 Fixtures & Equipment Supply | 0 | 0 | 0 | 340000 | 236533.26 | 0 | 0 | 0 | 0 | 340000 | 236533.26 | 0 | 340000 | 0 | 0 | Apprentice Lvl 1 | 8.25 | 409.94 | Apprentice Lvl 1-2 | Sprinkler | 03 Rough-in (Labour) | Journeyman Lvl 2 | Journeyman Lvl 1-2
| Margin at committed cost, after overhead |  | -0.5508% | Equipment / tools | 2182.13 | 0.02391% |  |  |  | P - BLDG A - L1 Plumbing Finishing (Labour) | P | 04 Finishing (Labour) | 0 | 30000 | 536.04 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 536.04 | 30000 | 0 | 0 | 0 | Apprentice Lvl 4 | 774.5 | 29422.34 | Apprentice Lvl 3-6 | Finishing | 04 Finishing (Labour) | Foreman Lvl 1 | Foreman & PM
| Overhead counts hours so far only; remaining hours add more. | [8 empty] | P - BLDG A - L2 Plumbing Finishing (Labour) | P | 04 Finishing (Labour) | 0 | 30000 | 1271.84 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 1271.84 | 30000 | 0 | 0 | 0 | Journeyman Lvl 1 | 8.25 | 0 | Journeyman Lvl 1-2 | Material Supply | 05 Material Supply | Foreman Lvl 2 | Foreman & PM
[10 empty] | P - BLDG A - L3 Plumbing Finishing (Labour) | P | 04 Finishing (Labour) | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 30000 | 0 | 0 | 0 | Foreman Lvl 1 | 68.75 | 4934.73 | Foreman & PM | Fixtures | 06 Fixtures & Equipment Supply | Project Manager | Foreman & PM
| Knowify phases all mapped | OK | [7 empty] | P - BLDG A - L4 Plumbing Finishing (Labour) | P | 04 Finishing (Labour) | 0 | 30000 | 15076.26 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 15076.26 | 30000 | 0 | 0 | 0 | Apprentice Lvl 1 | 127.5 | 6350.74 | Apprentice Lvl 1-2 | Equipment Supply | 06 Fixtures & Equipment Supply | HVAC Field Supervisor | Foreman & PM
| Knowify roles all mapped | OK | [7 empty] | P - BLDG A - L5 Plumbing Finishing (Labour) | P | 04 Finishing (Labour) | 0 | 30000 | 14799.4 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 14799.4 | 30000 | 0 | 0 | 0 | Journeyman Lvl 1 | 130.6667 | 5613.44 | Journeyman Lvl 1-2 | Mech Room | 06 Fixtures & Equipment Supply | Health & Safety Coordinator | Foreman & PM
[10 empty] | P - BLDG A - L6 Plumbing Finishing (Labour) | P | 04 Finishing (Labour) | 0 | 30000 | 19468.79 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 19468.79 | 30000 | 0 | 0 | 0 | Foreman Lvl 1 | 7.25 | 409.55 | Foreman & PM | Controls | 06 Fixtures & Equipment Supply | Divisional Manager | Foreman & PM
[10 empty] | P - BLDG B - L1 Plumbing Rough-in (Labour) | P | 03 Rough-in (Labour) | 1 | 40000 | 72622.68 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 72622.68 | 72622.68 | 0 | 0 | 0 | Apprentice Lvl 1 | 1321.0833 | 62909.07 | Apprentice Lvl 1-2 | Testing | 07 Testing, TAB & Commissioning | Admin | Foreman & PM
| HOW EACH PHASE RAN vs BUDGET (closed phases that used at least half their budget + phases already at/over budget; change orders excluded) | [8 empty] | P - BLDG B - L2 Plumbing Rough-in (Labour) | P | 03 Rough-in (Labour) | 1 | 40000 | 52429.5 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 52429.5 | 52429.5 | 0 | 0 | 0 | Apprentice Lvl 5 | 712.3333 | 41132.91 | Apprentice Lvl 3-6 | Commissioning | 07 Testing, TAB & Commissioning
| Div / Phase | # Phases | Labour Budget | Labour Actual | Labour Act/Bud | Material Budget | Material Actual | Material Act/Bud | Labour Hrs (est.) | P - BLDG B - L3 Plumbing Rough-in (Labour) | P | 03 Rough-in (Labour) | 1 | 40000 | 46912.2 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 46912.2 | 46912.2 | 0 | 0 | 0 | Journeyman Lvl 1 | 295.6667 | 21456.47 | Journeyman Lvl 1-2 | TAB | 07 Testing, TAB & Commissioning
| P 01 Shop Drawings, Permits & Mobilization | 1 | 4000 | 530.01 | 0.1325 | 1500 | 3203.97 | 2.136 | 10.4947 | P - BLDG B - L4 Plumbing Rough-in (Labour) | P | 03 Rough-in (Labour) | 1 | 40000 | 53561.64 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 53561.64 | 53561.64 | 0 | 0 | 0 | HVAC Field Supervisor | 296 | 19846.2 | Foreman & PM | Completion | 08 Completion & Final Documents
| P 02 Foundation & Underground | 1 | 35000 | 60524.63 | 1.7293 | 125000 | 127755.62 | 1.022 | 1198.4433 | P - BLDG B - L5 Plumbing Rough-in (Labour) | P | 03 Rough-in (Labour) | 1 | 40000 | 67839.85 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 67839.85 | 67839.85 | 0 | 0 | 0 | Apprentice Lvl 3 | 670.9167 | 35887.26 | Apprentice Lvl 3-6 | Final Doc | 08 Completion & Final Documents
| P 03 Rough-in (Labour) | 12 | 480000 | 647639.94 | 1.3492 | 0 | 0 |  | 12823.8658 | P - BLDG B - L6 Plumbing Rough-in (Labour) | P | 03 Rough-in (Labour) | 1 | 40000 | 81402.13 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 81402.13 | 81402.13 | 0 | 0 | 0 | Apprentice Lvl 2 | 524 | 15622.92 | Apprentice Lvl 1-2 | Office | 09 Office, Supervision & General
| P 04 Finishing (Labour) | 0 | 0 | 0 |  | 0 | 0 |  | 0 | P - BLDG B - Roof Plumbing (Labour & Material) | P | 03 Rough-in (Labour) | 0 | 27600 | 0 | 12400 | 569.49 | 0 | 0 | 0 | 0 | 40000 | 569.49 | 27600 | 12400 | 0 | 0 | Foreman Lvl 1 | 1594.4167 | 106764.29 | Foreman & PM | Safety | 09 Office, Supervision & General
| P 05 Material Supply | 2 | 0 | 0 |  | 400000 | 516964.94 | 1.2924 | 0 | P - BLDG B - Material Supply | P | 05 Material Supply | 1 | 0 | 0 | 200000 | 253019.4 | 0 | 0 | 0 | 0 | 200000 | 253019.4 | 0 | 253019.4 | 0 | 0 | Project Manager | 313.5 | 26841.87 | Foreman & PM | Supervision | 09 Office, Supervision & General
| P 06 Fixtures & Equipment Supply | 0 | 0 | 0 |  | 0 | 0 |  | 0 | P - BLDG B - Plumbing Fixtures & Access Panels Supply | P | 06 Fixtures & Equipment Supply | 0 | 0 | 0 | 340000 | 40501.95 | 0 | 0 | 0 | 0 | 340000 | 40501.95 | 0 | 340000 | 0 | 0 | Apprentice Lvl 2 | 328.5 | 17953.45 | Apprentice Lvl 1-2
| P 07 Testing, TAB & Commissioning | 0 | 0 | 0 |  | 0 | 0 |  | 0 | P - BLDG B - L1 Plumbing Finishing (Labour) | P | 04 Finishing (Labour) | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 30000 | 0 | 0 | 0 | Apprentice Lvl 1 | 523.4167 | 23983.24 | Apprentice Lvl 1-2
| P 08 Completion & Final Documents | 0 | 0 | 0 |  | 0 | 0 |  | 0 | P - BLDG B - L2 Plumbing Finishing (Labour) | P | 04 Finishing (Labour) | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 30000 | 0 | 0 | 0 | Apprentice Lvl 2 | 233.25 | 6486.69 | Apprentice Lvl 1-2
| P 09 Office, Supervision & General | 0 | 0 | 0 |  | 0 | 0 |  | 0 | P - BLDG B - L3 Plumbing Finishing (Labour) | P | 04 Finishing (Labour) | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 30000 | 0 | 0 | 0 | Foreman Lvl 1 | 683.75 | 38447.43 | Foreman & PM
| H 01 Shop Drawings, Permits & Mobilization | 0 | 0 | 0 |  | 0 | 0 |  | 0 | P - BLDG B - L4 Plumbing Finishing (Labour) | P | 04 Finishing (Labour) | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 30000 | 0 | 0 | 0 | Journeyman Lvl 2 | 810 | 49501.04 | Journeyman Lvl 1-2
| H 02 Foundation & Underground | 0 | 0 | 0 |  | 0 | 0 |  | 0 | P - BLDG B - L5 Plumbing Finishing (Labour) | P | 04 Finishing (Labour) | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 30000 | 0 | 0 | 0 | Journeyman Lvl 2 | 419.5 | 28117.47 | Journeyman Lvl 1-2
| H 03 Rough-in (Labour) | 0 | 0 | 0 |  | 0 | 0 |  | 0 | P - BLDG B - L6 Plumbing Finishing (Labour) | P | 04 Finishing (Labour) | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 30000 | 0 | 0 | 0 | Apprentice Lvl 3 | 16.0833 | 799.66 | Apprentice Lvl 3-6
| H 04 Finishing (Labour) | 0 | 0 | 0 |  | 0 | 0 |  | 0 | P - Mech Room & Equipment Supply | P | 06 Fixtures & Equipment Supply | 0 | 0 | 0 | 760000 | 309140.5 | 0 | 0 | 0 | 0 | 760000 | 309140.5 | 0 | 760000 | 0 | 0 | Apprentice Lvl 8 | 1233.8333 | 64611.83 | Apprentice Lvl 7-8
| H 05 Material Supply | 0 | 0 | 0 |  | 0 | 0 |  | 0 | P - Insulation and Heat Trace | P | 03 Rough-in (Labour) | 0 | 0 | 0 | 0 | 0 | 490000 | 248585.15 | 0 | 0 | 490000 | 248585.15 | 0 | 0 | 490000 | 0 | Apprentice Lvl 1 | 742 | 23704.44 | Apprentice Lvl 1-2
| H 06 Fixtures & Equipment Supply | 0 | 0 | 0 |  | 0 | 0 |  | 0 | P - Permits | P | 01 Shop Drawings, Permits & Mobilization | 0 | 0 | 0 | 45000 | 44966.8 | 0 | 0 | 0 | 0 | 45000 | 44966.8 | 0 | 45000 | 0 | 0 | Apprentice Lvl 3 | 179.5 | 10109.44 | Apprentice Lvl 3-6
| H 07 Testing, TAB & Commissioning | 0 | 0 | 0 |  | 0 | 0 |  | 0 | P - Shop Drawings, and Mobilization | P | 01 Shop Drawings, Permits & Mobilization | 0 | 8000 | 0 | 49000 | 37366.65 | 3000 | 0 | 0 | 444.69 | 60000 | 37811.34 | 8000 | 49000 | 3000 | 444.69 | Apprentice Lvl 1 | 238.1667 | 8756.04 | Apprentice Lvl 1-2
| H 08 Completion & Final Documents | 0 | 0 | 0 |  | 0 | 0 |  | 0 | P - Completion & Final Documents | P | 08 Completion & Final Documents | 0 | 18000 | 0 | 29000 | 363.16 | 48000 | 0 | 0 | 0 | 95000 | 363.16 | 18000 | 29000 | 48000 | 0 | Apprentice Level 6 | 900.1667 | 44746.28 | Apprentice Lvl 3-6
| H 09 Office, Supervision & General | 0 | 0 | 0 |  | 0 | 0 |  | 0 | HVAC - Parkade HVAC (Labour & Material) | V | 03 Rough-in (Labour) | 0 | 81000 | 9668.29 | 48000 | 53851.47 | 11000 | 0 | 0 | 123.79 | 140000 | 63643.55 | 81000 | 53851.47 | 11000 | 123.79 | Apprentice Lvl 1 | 20.5 | 748.05 | Apprentice Lvl 1-2
| V 01 Shop Drawings, Permits & Mobilization | 0 | 0 | 0 |  | 0 | 0 |  | 0 | V - BLDG A - L1 HVAC Rough-in (Labour) | V | 03 Rough-in (Labour) | 1 | 25000 | 42644.91 | 0 | 0 | 0 | 10552.5 | 0 | 191.5 | 25000 | 53388.91 | 42644.91 | 0 | 10552.5 | 191.5 | Divisional Manager | 9 | 866.07 | Foreman & PM
| V 02 Foundation & Underground | 0 | 0 | 0 |  | 0 | 0 |  | 0 | V - BLDG A - L2 HVAC Rough-in (Labour) | V | 03 Rough-in (Labour) | 1 | 25000 | 38643.68 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 38643.68 | 38643.68 | 0 | 0 | 0 | Apprentice Lvl 2 | 46.6667 | 2636.69 | Apprentice Lvl 1-2
| V 03 Rough-in (Labour) | 12 | 300000 | 518488.26 | 1.7283 | 0 | 20243.83 |  | 10266.5438 | V - BLDG A - L3 HVAC Rough-in (Labour) | V | 03 Rough-in (Labour) | 1 | 25000 | 45778.31 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 45778.31 | 45778.31 | 0 | 0 | 0 | Apprentice Lvl 5 | 885.3333 | 35045.34 | Apprentice Lvl 3-6
| V 04 Finishing (Labour) | 1 | 5500 | 0 | 0 | 0 | 9879.96 |  | 0 | V - BLDG A - L4 HVAC Rough-in (Labour) | V | 03 Rough-in (Labour) | 1 | 25000 | 37075.2 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 37075.2 | 37075.2 | 0 | 0 | 0 | Journeyman Lvl 2 | 16.5 | 1193.44 | Journeyman Lvl 1-2
| V 05 Material Supply | 2 | 0 | 0 |  | 150000 | 283784.62 | 1.8919 | 0 | V - BLDG A - L5 HVAC Rough-in (Labour) | V | 03 Rough-in (Labour) | 1 | 25000 | 50793.2 | 0 | 4215.13 | 0 | 0 | 0 | 0 | 25000 | 55008.33 | 50793.2 | 4215.13 | 0 | 0 | Journeyman | 120.75 | 8318.48 | Journeyman Lvl 1-2
| V 06 Fixtures & Equipment Supply | 0 | 0 | 0 |  | 0 | 0 |  | 0 | V - BLDG A - L6 HVAC Rough-in (Labour) | V | 03 Rough-in (Labour) | 1 | 25000 | 45388.62 | 0 | 10358.7 | 0 | 0 | 0 | 0 | 25000 | 55747.32 | 45388.62 | 10358.7 | 0 | 0 | Apprentice Lvl 8 | 133.9167 | 6745.85 | Apprentice Lvl 7-8
| V 07 Testing, TAB & Commissioning | 0 | 0 | 0 |  | 0 | 0 |  | 0 | V - BLDG A - Material Supply | V | 05 Material Supply | 1 | 0 | 0 | 75000 | 158960.4 | 0 | 0 | 0 | 0 | 75000 | 158960.4 | 0 | 158960.4 | 0 | 0 | Admin | 2.75 | 192.75 | Foreman & PM
| V 08 Completion & Final Documents | 0 | 0 | 0 |  | 0 | 0 |  | 0 | V - BLDG A - L1 HVAC Finishing (Labour) | V | 04 Finishing (Labour) | 0 | 5500 | 126.45 | 0 | 0 | 0 | 0 | 0 | 0 | 5500 | 126.45 | 5500 | 0 | 0 | 0 | Foreman Lvl 1 | 252 | 15157.05 | Foreman & PM
| V 09 Office, Supervision & General | 0 | 0 | 0 |  | 0 | 0 |  | 0 | V - BLDG A - L2 HVAC Finishing (Labour) | V | 04 Finishing (Labour) | 0 | 5500 | 497.31 | 0 | 0 | 0 | 0 | 0 | 0 | 5500 | 497.31 | 5500 | 0 | 0 | 0 | Apprentice Lvl 3 | 932.3333 | 39632.42 | Apprentice Lvl 3-6
| AC 01 Shop Drawings, Permits & Mobilization | 0 | 0 | 0 |  | 0 | 0 |  | 0 | V - BLDG A - L3 HVAC Finishing (Labour) | V | 04 Finishing (Labour) | 0 | 5500 | 950.79 | 0 | 0 | 0 | 0 | 0 | 0 | 5500 | 950.79 | 5500 | 0 | 0 | 0 | Project Manager | 707.0833 | 54979.27 | Foreman & PM
| AC 02 Foundation & Underground | 0 | 0 | 0 |  | 0 | 0 |  | 0 | V - BLDG A - L4 HVAC Finishing (Labour) | V | 04 Finishing (Labour) | 0 | 5500 | 1288.36 | 0 | 0 | 0 | 0 | 0 | 0 | 5500 | 1288.36 | 5500 | 0 | 0 | 0 | Foreman Lvl 1 | 142.3333 | 8954.22 | Foreman & PM
| AC 03 Rough-in (Labour) | 0 | 0 | 0 |  | 0 | 0 |  | 0 | V - BLDG A - L5 HVAC Finishing (Labour) | V | 04 Finishing (Labour) | 0 | 5500 | 3313 | 0 | 0 | 0 | 0 | 0 | 0 | 5500 | 3313 | 5500 | 0 | 0 | 0 | Apprentice Lvl 1 | 828.8333 | 22463.59 | Apprentice Lvl 1-2
| AC 04 Finishing (Labour) | 0 | 0 | 0 |  | 0 | 0 |  | 0 | V - BLDG A - L6 HVAC Finishing (Labour) | V | 04 Finishing (Labour) | 0 | 5500 | 2389.33 | 0 | 0 | 0 | 0 | 0 | 0 | 5500 | 2389.33 | 5500 | 0 | 0 | 0 | Apprentice Lvl 4 | 598.5833 | 33027.75 | Apprentice Lvl 3-6
| AC 05 Material Supply | 0 | 0 | 0 |  | 0 | 0 |  | 0 | V - BLDG B - L1 HVAC Rough-in (Labour) | V | 03 Rough-in (Labour) | 1 | 25000 | 53184.92 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 53184.92 | 53184.92 | 0 | 0 | 0 | Apprentice Lvl 1 | 82.5 | 4043.3 | Apprentice Lvl 1-2
| AC 06 Fixtures & Equipment Supply | 0 | 0 | 0 |  | 0 | 0 |  | 0 | V - BLDG B - L2 HVAC Rough-in (Labour) | V | 03 Rough-in (Labour) | 1 | 25000 | 34806.17 | 0 | 0 | 0 | 7323.75 | 0 | 0 | 25000 | 42129.92 | 34806.17 | 0 | 7323.75 | 0 | Apprentice Lvl 2 | 32.5 | 1683.82 | Apprentice Lvl 1-2
| AC 07 Testing, TAB & Commissioning | 0 | 0 | 0 |  | 0 | 0 |  | 0 | HVAC - BLDG 2 - L3 HVAC Rough-in (Labour) | V | 03 Rough-in (Labour) | 1 | 25000 | 34916.82 | 0 | 5670 | 0 | 0 | 0 | 0 | 25000 | 40586.82 | 34916.82 | 5670 | 0 | 0 | Foreman Lvl 1 | 6.25 | 499.25 | Foreman & PM
| AC 08 Completion & Final Documents | 0 | 0 | 0 |  | 0 | 0 |  | 0 | V - BLDG B - L4 HVAC Rough-in (Labour) | V | 03 Rough-in (Labour) | 1 | 25000 | 43850.78 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 43850.78 | 43850.78 | 0 | 0 | 0 | Apprentice Lvl 2 | 170.75 | 7304.96 | Apprentice Lvl 1-2
| AC 09 Office, Supervision & General | 0 | 0 | 0 |  | 0 | 0 |  | 0 | V - BLDG B - L5 HVAC Rough-in (Labour) | V | 03 Rough-in (Labour) | 1 | 25000 | 49872.87 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 49872.87 | 49872.87 | 0 | 0 | 0 | Apprentice Lvl 1 | 224.5833 | 4409.79 | Apprentice Lvl 1-2
[10 empty] | V - BLDG B - L6 HVAC Rough-in (Labour) | V | 03 Rough-in (Labour) | 1 | 25000 | 41532.78 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 41532.78 | 41532.78 | 0 | 0 | 0 | Apprentice Lvl 2 | 746.75 | 32916.38 | Apprentice Lvl 1-2
[10 empty] | V - BLDG B - Material Supply | V | 05 Material Supply | 1 | 0 | 0 | 75000 | 124824.22 | 0 | 2535.75 | 0 | 0 | 75000 | 127359.97 | 0 | 124824.22 | 2535.75 | 0 | Apprentice Lvl 7 | 518.1667 | 21871.27 | Apprentice Lvl 7-8
| ACTUAL CREW (KNOWIFY TIME, all trades) | [8 empty] | V - BLDG B - L1 HVAC Finishing | V | 04 Finishing (Labour) | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5500 | 0 | 5500 | 0 | 0 | 0 | Health & Safety Coordinator | 237 | 15506.57 | Foreman & PM
| Crew Class | Hours | Cost | Actual $/hr | Actual Mix | Template Mix (P&H) |  |  |  | V - BLDG B - L2 HVAC Finishing | V | 04 Finishing (Labour) | 1 | 5500 | 0 | 0 | 9879.96 | 0 | 0 | 0 | 0 | 5500 | 9879.96 | 5500 | 9879.96 | 0 | 0 | Apprentice Lvl 3 | 283.5 | 9134.52 | Apprentice Lvl 3-6
| Apprentice Lvl 1-2 | 11897.6667 | 478867.9 | 40.2489 | 36.47% | 40% |  |  |  | V - BLDG B - L3 HVAC Finishing | V | 04 Finishing (Labour) | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5500 | 0 | 5500 | 0 | 0 | 0 | Apprentice Lvl 1 | 643.6667 | 20927.67 | Apprentice Lvl 1-2
| Apprentice Lvl 3-6 | 8149.6667 | 383866.72 | 47.1021 | 24.98% | 30% |  |  |  | V - BLDG B - L4 HVAC Finishing | V | 04 Finishing (Labour) | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5500 | 0 | 5500 | 0 | 0 | 0 | Foreman Lvl 1 | 272.5 | 21674.75 | Foreman & PM
| Apprentice Lvl 7-8 | 2798.25 | 143306.89 | 51.213 | 8.578% | 5% |  |  |  | V - BLDG B - L5 HVAC Finishing | V | 04 Finishing (Labour) | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5500 | 0 | 5500 | 0 | 0 | 0 | Apprentice Lvl 3 | 32.5 | 1680.9 | Apprentice Lvl 3-6
| Journeyman Lvl 1-2 | 3917.9167 | 241134.17 | 61.5465 | 12.01% | 11% |  |  |  | V - BLDG B - L6 HVAC Finishing | V | 04 Finishing (Labour) | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5500 | 0 | 5500 | 0 | 0 | 0 | Apprentice Lvl 8 | 912.3333 | 50077.94 | Apprentice Lvl 7-8
| Foreman & PM | 5857.4167 | 400268.93 | 68.3354 | 17.96% | 14% |  |  |  | V - Ventilation Equipment Supply | V | 06 Fixtures & Equipment Supply | 0 | 0 | 0 | 420000 | 309964.09 | 0 | 0 | 0 | 0 | 420000 | 309964.09 | 0 | 420000 | 0 | 0 | Apprentice Lvl 1 | 571 | 21615.58 | Apprentice Lvl 1-2
| Unmapped | 0 | 0 | 0 | 0% |  |  |  |  | V - HVAC Controls | V | 06 Fixtures & Equipment Supply | 0 | 0 | 0 | 0 | 0 | 290000 | 140398.65 | 0 | 0 | 290000 | 140398.65 | 0 | 0 | 290000 | 0 | Apprentice Lvl 4 | 654.75 | 35530.73 | Apprentice Lvl 3-6
| TOTAL / BLENDED | 32620.9167 | 1647444.61 | 50.5027 | 100% |  |  |  |  | V - TAB and Commissioning | V | 07 Testing, TAB & Commissioning | 0 | 0 | 0 | 0 | 0 | 70000 | 0 | 0 | 0 | 70000 | 0 | 0 | 0 | 70000 | 0 | Apprentice Lvl 4 | 153.5 | 5875.98 | Apprentice Lvl 3-6
| Knowify cost per hour as recorded in Knowify. Confirm whether it includes full burden. | [8 empty] | V - Permit, Shop Drawings and Mobilization | V | 01 Shop Drawings, Permits & Mobilization | 0 | 4000 | 0 | 5000 | 9893.51 | 4000 | 2870.7 | 0 | 0 | 13000 | 12764.21 | 4000 | 9893.51 | 4000 | 0 | Apprentice Lvl 5 | 619.1667 | 22787.82 | Apprentice Lvl 3-6
[10 empty] | V - Insulation Labour | V | 03 Rough-in (Labour) | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 50000 | 0 |  | 0 | 0
[10 empty] | V - Completion & Final Documents | V | 08 Completion & Final Documents | 0 | 2500 | 0 | 7500 | 0 | 3500 | 0 | 0 | 0 | 13500 | 0 | 2500 | 7500 | 3500 | 0 |  | 0 | 0
[10 empty] | V - Roof HVAC | V | 03 Rough-in (Labour) | 0 | 4000 | 1267.55 | 6000 | 77.28 | 0 | 0 | 0 | 0 | 10000 | 1344.83 | 4000 | 6000 | 0 | 0 |  | 0 | 0
[10 empty] | P - Plumbing Office | P | 09 Office, Supervision & General | 0 | 0 | 53112.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53112.89 | 53112.89 | 0 | 0 | 0 |  | 0 | 0
[10 empty] | HVAC - HVAC Office | V | 09 Office, Supervision & General | 0 | 0 | 27629.64 | 0 | 470.4 | 0 | 0 | 0 | 0 | 0 | 28100.04 | 27629.64 | 470.4 | 0 | 0 |  | 0 | 0
[10 empty] | Safety | Other | 09 Office, Supervision & General | 0 | 0 | 14267.73 | 0 | 879.75 | 0 | 0 | 0 | 0 | 0 | 15147.48 | 14267.73 | 879.75 | 0 | 0 |  | 0 | 0
[10 empty] | CO-01 [COR-01] P -Drainage Channel Revision | Other | Excluded | 0 | 0 | 0 | 2220 | 0 | 0 | 0 | 0 | 0 | 2220 | 0 | 0 | 2220 | 0 | 0 |  | 0 | 0
[10 empty] | CO-02 [COR-02] P - MSI-1 Changes | Other | Excluded | 0 | 5200 | 2715.77 | 8400 | 77.28 | 0 | 0 | 0 | 0 | 13600 | 2793.05 | 5200 | 8400 | 0 | 0 |  | 0 | 0
[10 empty] | CO-03&5 [COR-06] VRF Heating System | Other | Excluded | 0 | 605000 | 135843.55 | 1008000 | 784791.25 | 275000 | 230711.27 | 0 | 0 | 1888000 | 1151346.07 | 605000 | 1008000 | 275000 | 0 |  | 0 | 0
[10 empty] | CO-04 [COR-04] P - MSI-04 SI-008 Ground Floor Drains | Other | Excluded | 0 | 2900 | 0 | 2900 | 0 | 200 | 0 | 0 | 0 | 6000 | 0 | 2900 | 2900 | 200 | 0 |  | 0 | 0
[10 empty] | CO-06 [COR-05] (Part 2) V - Elevator Machine Room Cooling | Other | Excluded | 0 | 3500 | 176.13 | 13300 | 11655 | 3200 | 0 | 0 | 0 | 20000 | 11831.13 | 3500 | 13300 | 3200 | 0 |  | 0 | 0
[10 empty] | CO-7 [COR-07] V - Amenity Ceiling Fan coils | Other | Excluded | 0 | 1300 | 0 | 7500 | 0 | 2400 | 0 | 0 | 0 | 11200 | 0 | 1300 | 7500 | 2400 | 0 |  | 0 | 0
[10 empty] | CO-8 [COR-08] P - Planter drain pipe rerouting | Other | Excluded | 0 | 13500 | 3829.39 | 10860 | 0 | 0 | 0 | 0 | 0 | 24360 | 3829.39 | 13500 | 10860 | 0 | 0 |  | 0 | 0
[10 empty] | [COR-09] P - Insulation & HT to Attic HB's for Building A & B | Other | 03 Rough-in (Labour) | 0 | 0 | 0 | 0 | 0 | 5391 | 5390.31 | 0 | 0 | 5391 | 5390.31 | 0 | 0 | 5391 | 0 |  | 0 | 0
[10 empty] | CO-10 [COR-10] P - ASI-017 – Unit C5 Ensuite Tub to Shower | Other | Excluded | 0 | 0 | 0 | -2278.59 | 0 | 0 | 0 | 0 | 0 | -2278.59 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[10 empty] | CO-11 [COR-05] (Part 1) P - Credit for Drinking Fountain | Other | Excluded | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3762.87 | 0 | -3762.87 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[10 empty] | CO-12 [COR-12] P - RFI-13 Drain discharge to tank | Other | Excluded | 0 | -1830 | 0 | -740 | 430.1 | 0 | 0 | 0 | 0 | -2570 | 430.1 | 0 | 430.1 | 0 | 0 |  | 0 | 0
[10 empty] | [COR-17] (P) Replacement of Damaged Shower – 60 x 30 RH (60135 A) | Other | Excluded | 0 | 0 | 0 | 488 | 0 | 0 | 0 | 0 | 0 | 488 | 0 | 0 | 488 | 0 | 0 |  | 0 | 0
[10 empty] | COR-15 (P) Sediment interceptor for MSI-10 R2 | Other | Excluded | 0 | 1900 | 1649.39 | 4400 | 4620 | 0 | 0 | 0 | 0 | 6300 | 6269.39 | 1900 | 4620 | 0 | 0 |  | 0 | 0
[10 empty] | CO-16 [COR-11] V - MS1-02 R2 Duct & FD-Trap Primer | Other | Excluded | 0 | 900 | 0 | 4530 | 0 | 0 | 0 | 0 | 0 | 5430 | 0 | 900 | 4530 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## KNOWIFY PHASES
|  |  |  | Total Cost |  |  | Materials |  |  | Labor |  |  | Subcontractors |  |  | Equipment |  |  | Miscellanea
Phase | Status | Progress | Cost vs Budget | Cost to Date | Budgeted | Remaining | Cost to Date | Budgeted | Remaining | Cost to Date | Budgeted | Remaining | Cost to Date | Budgeted | Remaining | Cost to Date | Budgeted | Remaining | Cost to Date | Budgeted | Remaining
Fire Sprinklers | Active |  | 0.8865 | 833305.74 | 940000 | 106694.26 | 0 | 0 | 0 | 0 | 0 | 0 | 833305.74 | 940000 | 106694.26 | 0 | 0 | 0 | 0 | 0 | 0
P - Water Connection Temporary | Closed |  | 0.67891 | 3733.98 | 5500 | 1766.02 | 3203.97 | 1500 | -1703.97 | 530.01 | 4000 | 3469.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P - Foundation Plumbing & Sumps | Closed |  | 1.1768 | 188280.25 | 160000 | -28280.25 | 127755.62 | 125000 | -2755.62 | 60524.63 | 35000 | -25524.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P - Parkade Plumbing (Labour & Material) | Active |  | 0.95709 | 172275.36 | 180000 | 7724.64 | 60999.27 | 110000 | 49000.73 | 109892.33 | 70000 | -39892.33 | 0 | 0 | 0 | 1383.76 | 0 | -1383.76 | 0 | 0 | 0
P - BLDG A - L1 Plumbing Rough-in (Labour) | Active |  | 1.9742 | 78969.73 | 40000 | -38969.73 | 0 | 0 | 0 | 78969.73 | 40000 | -38969.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P - BLDG A - L2 Plumbing Rough-in (Labour) | Active |  | 1.1031 | 44124.47 | 40000 | -4124.47 | 0 | 0 | 0 | 44124.47 | 40000 | -4124.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P - BLDG A - L3 Plumbing Rough-in (Labour) | Closed |  | 1.0555 | 42219.99 | 40000 | -2219.99 | 0 | 0 | 0 | 37888.74 | 40000 | 2111.26 | 4331.25 | 0 | -4331.25 | 0 | 0 | 0 | 0 | 0 | 0
P - BLDG A - L4 Plumbing Rough-in (Labour) | Closed |  | 1.0908 | 43632.52 | 40000 | -3632.52 | 0 | 0 | 0 | 43632.52 | 40000 | -3632.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P - BLDG A - L5 Plumbing Rough-in (Labour) | Closed |  | 0.96362 | 38544.91 | 40000 | 1455.09 | 0 | 0 | 0 | 38544.91 | 40000 | 1455.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P - BLDG A - L6 Plumbing Rough-in (Labour) | Closed |  | 0.74279 | 29711.57 | 40000 | 10288.43 | 0 | 0 | 0 | 29711.57 | 40000 | 10288.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P - BLDG A - Roof Plumbing (Labour & Material) | Closed |  | 0.012289 | 491.54 | 40000 | 39508.46 | 0 | 12400 | 12400 | 491.54 | 27600 | 27108.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P - BLDG A - Material Supply | Active |  | 1.3199 | 263983.93 | 200000 | -63983.93 | 263945.54 | 200000 | -63945.54 | 0 | 0 | 0 | 0 | 0 | 0 | 38.39 | 0 | -38.39 | 0 | 0 | 0
P - BLDG A - Plumbing Fixtures & Access Panels Supply | Active |  | 0.69569 | 236533.26 | 340000 | 103466.74 | 236533.26 | 340000 | 103466.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P - BLDG A - L1 Plumbing Finishing (Labour) | Closed |  | 0.017868 | 536.04 | 30000 | 29463.96 | 0 | 0 | 0 | 536.04 | 30000 | 29463.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P - BLDG A - L2 Plumbing Finishing (Labour) | Closed |  | 0.042395 | 1271.84 | 30000 | 28728.16 | 0 | 0 | 0 | 1271.84 | 30000 | 28728.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P - BLDG A - L3 Plumbing Finishing (Labour) | Closed |  | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P - BLDG A - L4 Plumbing Finishing (Labour) | Active |  | 0.50254 | 15076.26 | 30000 | 14923.74 | 0 | 0 | 0 | 15076.26 | 30000 | 14923.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P - BLDG A - L5 Plumbing Finishing (Labour) | Active |  | 0.49331 | 14799.4 | 30000 | 15200.6 | 0 | 0 | 0 | 14799.4 | 30000 | 15200.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P - BLDG A - L6 Plumbing Finishing (Labour) | Active |  | 0.64896 | 19468.79 | 30000 | 10531.21 | 0 | 0 | 0 | 19468.79 | 30000 | 10531.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P - BLDG B - L1 Plumbing Rough-in (Labour) | Active |  | 1.8156 | 72622.68 | 40000 | -32622.68 | 0 | 0 | 0 | 72622.68 | 40000 | -32622.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P - BLDG B - L2 Plumbing Rough-in (Labour) | Active |  | 1.3107 | 52429.5 | 40000 | -12429.5 | 0 | 0 | 0 | 52429.5 | 40000 | -12429.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P - BLDG B - L3 Plumbing Rough-in (Labour) | Active |  | 1.1728 | 46912.2 | 40000 | -6912.2 | 0 | 0 | 0 | 46912.2 | 40000 | -6912.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P - BLDG B - L4 Plumbing Rough-in (Labour) | Active |  | 1.339 | 53561.64 | 40000 | -13561.64 | 0 | 0 | 0 | 53561.64 | 40000 | -13561.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P - BLDG B - L5 Plumbing Rough-in (Labour) | Active |  | 1.696 | 67839.85 | 40000 | -27839.85 | 0 | 0 | 0 | 67839.85 | 40000 | -27839.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P - BLDG B - L6 Plumbing Rough-in (Labour) | Active |  | 2.0351 | 81402.13 | 40000 | -41402.13 | 0 | 0 | 0 | 81402.13 | 40000 | -41402.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P - BLDG B - Roof Plumbing (Labour & Material) | Active |  | 0.014237 | 569.49 | 40000 | 39430.51 | 569.49 | 12400 | 11830.51 | 0 | 27600 | 27600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P - BLDG B - Material Supply | Active |  | 1.2651 | 253019.4 | 200000 | -53019.4 | 253019.4 | 200000 | -53019.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P - BLDG B - Plumbing Fixtures & Access Panels Supply | Active |  | 0.11912 | 40501.95 | 340000 | 299498.05 | 40501.95 | 340000 | 299498.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P - BLDG B - L1 Plumbing Finishing (Labour) | Closed |  | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P - BLDG B - L2 Plumbing Finishing (Labour) | Closed |  | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P - BLDG B - L3 Plumbing Finishing (Labour) | Closed |  | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P - BLDG B - L4 Plumbing Finishing (Labour) | Closed |  | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P - BLDG B - L5 Plumbing Finishing (Labour) | Closed |  | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P - BLDG B - L6 Plumbing Finishing (Labour) | Closed |  | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P - Mech Room & Equipment Supply | Active |  | 0.40676 | 309140.5 | 760000 | 450859.5 | 309140.5 | 760000 | 450859.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P - Insulation and Heat Trace | Active |  | 0.50732 | 248585.15 | 490000 | 241414.85 | 0 | 0 | 0 | 0 | 0 | 0 | 248585.15 | 490000 | 241414.85 | 0 | 0 | 0 | 0 | 0 | 0
P - Permits | Active |  | 0.99926 | 44966.8 | 45000 | 33.2 | 44966.8 | 45000 | 33.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P - Shop Drawings, and Mobilization | Active |  | 0.63019 | 37811.34 | 60000 | 22188.66 | 37366.65 | 49000 | 11633.35 | 0 | 8000 | 8000 | 0 | 3000 | 3000 | 444.69 | 0 | -444.69 | 0 | 0 | 0
P - Completion & Final Documents | Active |  | 0.0038227 | 363.16 | 95000 | 94636.84 | 363.16 | 29000 | 28636.84 | 0 | 18000 | 18000 | 0 | 48000 | 48000 | 0 | 0 | 0 | 0 | 0 | 0
HVAC - Parkade HVAC (Labour & Material) | Active |  | 0.4546 | 63643.55 | 140000 | 76356.45 | 53851.47 | 48000 | -5851.47 | 9668.29 | 81000 | 71331.71 | 0 | 11000 | 11000 | 123.79 | 0 | -123.79 | 0 | 0 | 0
V - BLDG A - L1 HVAC Rough-in (Labour) | Active |  | 2.1356 | 53388.91 | 25000 | -28388.91 | 0 | 0 | 0 | 42644.91 | 25000 | -17644.91 | 10552.5 | 0 | -10552.5 | 191.5 | 0 | -191.5 | 0 | 0 | 0
V - BLDG A - L2 HVAC Rough-in (Labour) | Active |  | 1.5457 | 38643.68 | 25000 | -13643.68 | 0 | 0 | 0 | 38643.68 | 25000 | -13643.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
V - BLDG A - L3 HVAC Rough-in (Labour) | Active |  | 1.8311 | 45778.31 | 25000 | -20778.31 | 0 | 0 | 0 | 45778.31 | 25000 | -20778.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
V - BLDG A - L4 HVAC Rough-in (Labour) | Active |  | 1.483 | 37075.2 | 25000 | -12075.2 | 0 | 0 | 0 | 37075.2 | 25000 | -12075.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
V - BLDG A - L5 HVAC Rough-in (Labour) | Active |  | 2.2003 | 55008.33 | 25000 | -30008.33 | 4215.13 | 0 | -4215.13 | 50793.2 | 25000 | -25793.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
V - BLDG A - L6 HVAC Rough-in (Labour) | Active |  | 2.2299 | 55747.32 | 25000 | -30747.32 | 10358.7 | 0 | -10358.7 | 45388.62 | 25000 | -20388.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
V - BLDG A - Material Supply | Active |  | 2.1195 | 158960.4 | 75000 | -83960.4 | 158960.4 | 75000 | -83960.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
V - BLDG A - L1 HVAC Finishing (Labour) | Active |  | 0.022991 | 126.45 | 5500 | 5373.55 | 0 | 0 | 0 | 126.45 | 5500 | 5373.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
V - BLDG A - L2 HVAC Finishing (Labour) | Active |  | 0.09042 | 497.31 | 5500 | 5002.69 | 0 | 0 | 0 | 497.31 | 5500 | 5002.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
V - BLDG A - L3 HVAC Finishing (Labour) | Active |  | 0.17287 | 950.79 | 5500 | 4549.21 | 0 | 0 | 0 | 950.79 | 5500 | 4549.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
V - BLDG A - L4 HVAC Finishing (Labour) | Active |  | 0.23425 | 1288.36 | 5500 | 4211.64 | 0 | 0 | 0 | 1288.36 | 5500 | 4211.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
V - BLDG A - L5 HVAC Finishing (Labour) | Active |  | 0.60236 | 3313 | 5500 | 2187 | 0 | 0 | 0 | 3313 | 5500 | 2187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
V - BLDG A - L6 HVAC Finishing (Labour) | Active |  | 0.43442 | 2389.33 | 5500 | 3110.67 | 0 | 0 | 0 | 2389.33 | 5500 | 3110.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
V - BLDG B - L1 HVAC Rough-in (Labour) | Active |  | 2.1274 | 53184.92 | 25000 | -28184.92 | 0 | 0 | 0 | 53184.92 | 25000 | -28184.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
V - BLDG B - L2 HVAC Rough-in (Labour) | Active |  | 1.6852 | 42129.92 | 25000 | -17129.92 | 0 | 0 | 0 | 34806.17 | 25000 | -9806.17 | 7323.75 | 0 | -7323.75 | 0 | 0 | 0 | 0 | 0 | 0
HVAC - BLDG 2 - L3 HVAC Rough-in (Labour) | Active |  | 1.6235 | 40586.82 | 25000 | -15586.82 | 5670 | 0 | -5670 | 34916.82 | 25000 | -9916.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
V - BLDG B - L4 HVAC Rough-in (Labour) | Active |  | 1.754 | 43850.78 | 25000 | -18850.78 | 0 | 0 | 0 | 43850.78 | 25000 | -18850.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
V - BLDG B - L5 HVAC Rough-in (Labour) | Active |  | 1.9949 | 49872.87 | 25000 | -24872.87 | 0 | 0 | 0 | 49872.87 | 25000 | -24872.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
V - BLDG B - L6 HVAC Rough-in (Labour) | Active |  | 1.6613 | 41532.78 | 25000 | -16532.78 | 0 | 0 | 0 | 41532.78 | 25000 | -16532.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
V - BLDG B - Material Supply | Active |  | 1.6981 | 127359.97 | 75000 | -52359.97 | 124824.22 | 75000 | -49824.22 | 0 | 0 | 0 | 2535.75 | 0 | -2535.75 | 0 | 0 | 0 | 0 | 0 | 0
V - BLDG B - L1 HVAC Finishing | Active |  | 0 | 0 | 5500 | 5500 | 0 | 0 | 0 | 0 | 5500 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
V - BLDG B - L2 HVAC Finishing | Active |  | 1.7964 | 9879.96 | 5500 | -4379.96 | 9879.96 | 0 | -9879.96 | 0 | 5500 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
V - BLDG B - L3 HVAC Finishing | Active |  | 0 | 0 | 5500 | 5500 | 0 | 0 | 0 | 0 | 5500 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
V - BLDG B - L4 HVAC Finishing | Active |  | 0 | 0 | 5500 | 5500 | 0 | 0 | 0 | 0 | 5500 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
V - BLDG B - L5 HVAC Finishing | Active |  | 0 | 0 | 5500 | 5500 | 0 | 0 | 0 | 0 | 5500 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
V - BLDG B - L6 HVAC Finishing | Active |  | 0 | 0 | 5500 | 5500 | 0 | 0 | 0 | 0 | 5500 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
V - Ventilation Equipment Supply | Active |  | 0.73801 | 309964.09 | 420000 | 110035.91 | 309964.09 | 420000 | 110035.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
V - HVAC Controls | Active |  | 0.48413 | 140398.65 | 290000 | 149601.35 | 0 | 0 | 0 | 0 | 0 | 0 | 140398.65 | 290000 | 149601.35 | 0 | 0 | 0 | 0 | 0 | 0
V - TAB and Commissioning | Active |  | 0 | 0 | 70000 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 70000 | 0 | 0 | 0 | 0 | 0 | 0
V - Permit, Shop Drawings and Mobilization | Active |  | 0.98186 | 12764.21 | 13000 | 235.79 | 9893.51 | 5000 | -4893.51 | 0 | 4000 | 4000 | 2870.7 | 4000 | 1129.3 | 0 | 0 | 0 | 0 | 0 | 0
V - Insulation Labour | Active |  | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0
V - Completion & Final Documents | Active |  | 0 | 0 | 13500 | 13500 | 0 | 7500 | 7500 | 0 | 2500 | 2500 | 0 | 3500 | 3500 | 0 | 0 | 0 | 0 | 0 | 0
V - Roof HVAC | Active |  | 0.13448 | 1344.83 | 10000 | 8655.17 | 77.28 | 6000 | 5922.72 | 1267.55 | 4000 | 2732.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P - Plumbing Office | Active |  | 0 | 53112.89 | 0 | -53112.89 | 0 | 0 | 0 | 53112.89 | 0 | -53112.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HVAC - HVAC Office | Active |  | 0 | 28100.04 | 0 | -28100.04 | 470.4 | 0 | -470.4 | 27629.64 | 0 | -27629.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Safety | Pending |  | 0 | 15147.48 | 0 | -15147.48 | 879.75 | 0 | -879.75 | 14267.73 | 0 | -14267.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CO-01 [COR-01] P -Drainage Channel Revision | Active |  | 0 | 0 | 2220 | 2220 | 0 | 2220 | 2220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CO-02 [COR-02] P - MSI-1 Changes | Active |  | 0.20537 | 2793.05 | 13600 | 10806.95 | 77.28 | 8400 | 8322.72 | 2715.77 | 5200 | 2484.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CO-03&5 [COR-06] VRF Heating System | Active |  | 0.60982 | 1151346.07 | 1888000 | 736653.93 | 784791.25 | 1008000 | 223208.75 | 135843.55 | 605000 | 469156.45 | 230711.27 | 275000 | 44288.73 | 0 | 0 | 0 | 0 | 0 | 0
CO-04 [COR-04] P - MSI-04 SI-008 Ground Floor Drains | Pending |  | 0 | 0 | 6000 | 6000 | 0 | 2900 | 2900 | 0 | 2900 | 2900 | 0 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0
CO-06 [COR-05] (Part 2) V - Elevator Machine Room Cooling | Pending |  | 0.59156 | 11831.13 | 20000 | 8168.87 | 11655 | 13300 | 1645 | 176.13 | 3500 | 3323.87 | 0 | 3200 | 3200 | 0 | 0 | 0 | 0 | 0 | 0
CO-7 [COR-07] V - Amenity Ceiling Fan coils | Pending |  | 0 | 0 | 11200 | 11200 | 0 | 7500 | 7500 | 0 | 1300 | 1300 | 0 | 2400 | 2400 | 0 | 0 | 0 | 0 | 0 | 0
CO-8 [COR-08] P - Planter drain pipe rerouting | Pending |  | 0.1572 | 3829.39 | 24360 | 20530.61 | 0 | 10860 | 10860 | 3829.39 | 13500 | 9670.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[COR-09] P - Insulation & HT to Attic HB's for Building A & B | Pending |  | 0.99987 | 5390.31 | 5391 | 0.69 | 0 | 0 | 0 | 0 | 0 | 0 | 5390.31 | 5391 | 0.69 | 0 | 0 | 0 | 0 | 0 | 0
CO-10 [COR-10] P - ASI-017 – Unit C5 Ensuite Tub to Shower | Pending |  | 0 | 0 | -2278.59 | -2278.59 | 0 | -2278.59 | -2278.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CO-11 [COR-05] (Part 1) P - Credit for Drinking Fountain | Pending |  | 0 | 0 | -3762.87 | -3762.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3762.87 | -3762.87 | 0 | 0 | 0
CO-12 [COR-12] P - RFI-13 Drain discharge to tank | Pending |  | -0.16735 | 430.1 | -2570 | -3000.1 | 430.1 | -740 | -1170.1 | 0 | -1830 | -1830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[COR-17] (P) Replacement of Damaged Shower – 60 x 30 RH (60135 A) | Pending |  | 0 | 0 | 488 | 488 | 0 | 488 | 488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COR-15 (P) Sediment interceptor for MSI-10 R2 | Pending |  | 0.99514 | 6269.39 | 6300 | 30.61 | 4620 | 4400 | -220 | 1649.39 | 1900 | 250.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CO-16 [COR-11] V - MS1-02 R2 Duct & FD-Trap Primer | Pending |  | 0 | 0 | 5430 | 5430 | 0 | 4530 | 4530 | 0 | 900 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## KNOWIFY TIME
Resource | Role | ST | Total | Cost | Avg. Hourly Cost
Employee 01 | Apprentice Lvl 3 | 24:00 | 24:00 | 1325.04 | 55.21
Employee 02 | Foreman Lvl 2 | 43:00 | 43:00 | 3550.5 | 82.57
Employee 03 | Apprentice Lvl 1 | 837:40 | 837:40 | 40180.24 | 47.97
Employee 04 | Foreman Lvl 2 | 1221:50 | 1221:50 | 81644.43 | 66.82
Employee 05 | Apprentice Lvl 1 | 0.125 | 0.125 | 82.74 | 27.58
Employee 06 | Apprentice Lvl 1 | 993:40 | 993:40 | 37200.9 | 37.44
Employee 07 | Apprentice Lvl 1 | 532:35 | 532:35 | 26480 | 49.72
Employee 08 | Apprentice Lvl 3 | 712:30 | 712:30 | 37728.33 | 52.95
Employee 09 | Journeyman Lvl 2 | 530:30 | 530:30 | 38320.57 | 72.23
Employee 10 | Journeyman Lvl 2 | 1586:05 | 1586:05 | 88613.26 | 55.87
Employee 11 | Apprentice Lvl 1 | 817:05 | 817:05 | 40619.1 | 49.71
Employee 12 | Apprentice Lvl 1 | 0.98958 | 0.98958 | 654.87 | 27.57
Employee 13 | Apprentice Lvl 2 | 1276:00 | 1276:00 | 48723.69 | 38.18
Employee 14 | Apprentice Lvl 1 | 0.34375 | 0.34375 | 409.94 | 49.69
Employee 15 | Apprentice Lvl 4 | 774:30 | 774:30 | 29422.34 | 37.99
Employee 16 | Journeyman Lvl 1 | 0.34375 | 0.34375 | 0 | 0
Employee 17 | Foreman Lvl 1 | 68:45 | 68:45 | 4934.73 | 71.78
Employee 18 | Apprentice Lvl 1 | 127:30 | 127:30 | 6350.74 | 49.81
Employee 19 | Journeyman Lvl 1 | 130:40 | 130:40 | 5613.44 | 42.96
Employee 20 | Foreman Lvl 1 | 0.30208 | 0.30208 | 409.55 | 56.49
Employee 21 | Apprentice Lvl 1 | 1321:05 | 1321:05 | 62909.07 | 47.62
Employee 22 | Apprentice Lvl 5 | 712:20 | 712:20 | 41132.91 | 57.74
Employee 23 | Journeyman Lvl 1 | 295:40 | 295:40 | 21456.47 | 72.57
Employee 24 | HVAC Field Supervisor | 296:00 | 296:00 | 19846.2 | 67.05
Employee 25 | Apprentice Lvl 3 | 670:55 | 670:55 | 35887.26 | 53.49
Employee 26 | Apprentice Lvl 2 | 524:00 | 524:00 | 15622.92 | 29.81
Employee 27 | Foreman Lvl 1 | 1594:25 | 1594:25 | 106764.29 | 66.96
Employee 28 | Project Manager | 313:30 | 313:30 | 26841.87 | 85.62
Employee 29 | Apprentice Lvl 2 | 328:30 | 328:30 | 17953.45 | 54.65
Employee 30 | Apprentice Lvl 1 | 523:25 | 523:25 | 23983.24 | 45.82
Employee 31 | Apprentice Lvl 2 | 233:15 | 233:15 | 6486.69 | 27.81
Employee 32 | Foreman Lvl 1 | 683:45 | 683:45 | 38447.43 | 56.23
Employee 33 | Journeyman Lvl 2 | 810:00 | 810:00 | 49501.04 | 61.11
Employee 34 | Journeyman Lvl 2 | 419:30 | 419:30 | 28117.47 | 67.03
Employee 35 | Apprentice Lvl 3 | 0.67014 | 0.67014 | 799.66 | 49.72
Employee 36 | Apprentice Lvl 8 | 1233:50 | 1233:50 | 64611.83 | 52.37
Employee 37 | Apprentice Lvl 1 | 742:00 | 742:00 | 23704.44 | 31.95
Employee 38 | Apprentice Lvl 3 | 179:30 | 179:30 | 10109.44 | 56.32
Employee 39 | Apprentice Lvl 1 | 238:10 | 238:10 | 8756.04 | 36.76
Employee 40 | Apprentice Level 6 | 900:10 | 900:10 | 44746.28 | 49.71
Employee 41 | Apprentice Lvl 1 | 0.85417 | 0.85417 | 748.05 | 36.49
Employee 42 | Divisional Manager | 0.375 | 0.375 | 866.07 | 96.23
Employee 43 | Apprentice Lvl 2 | 46:40 | 46:40 | 2636.69 | 56.5
Employee 44 | Apprentice Lvl 5 | 885:20 | 885:20 | 35045.34 | 39.58
Employee 45 | Journeyman Lvl 2 | 0.6875 | 0.6875 | 1193.44 | 72.33
Employee 46 | Journeyman | 120:45 | 120:45 | 8318.48 | 68.89
Employee 47 | Apprentice Lvl 8 | 133:55 | 133:55 | 6745.85 | 50.37
Employee 48 | Admin | 0.11458 | 0.11458 | 192.75 | 70.09
Employee 49 | Foreman Lvl 1 | 252:00 | 252:00 | 15157.05 | 60.15
Employee 50 | Apprentice Lvl 3 | 932:20 | 932:20 | 39632.42 | 42.51
Employee 51 | Project Manager | 707:05 | 707:05 | 54979.27 | 77.76
Employee 52 | Foreman Lvl 1 | 142:20 | 142:20 | 8954.22 | 62.91
Employee 53 | Apprentice Lvl 1 | 828:50 | 828:50 | 22463.59 | 27.1
Employee 54 | Apprentice Lvl 4 | 598:35 | 598:35 | 33027.75 | 55.18
Employee 55 | Apprentice Lvl 1 | 82:30 | 82:30 | 4043.3 | 49.01
Employee 56 | Apprentice Lvl 2 | 32:30 | 32:30 | 1683.82 | 51.81
Employee 57 | Foreman Lvl 1 | 0.26042 | 0.26042 | 499.25 | 79.88
Employee 58 | Apprentice Lvl 2 | 170:45 | 170:45 | 7304.96 | 42.78
Employee 59 | Apprentice Lvl 1 | 224:35 | 224:35 | 4409.79 | 19.64
Employee 60 | Apprentice Lvl 2 | 746:45 | 746:45 | 32916.38 | 44.08
Employee 61 | Apprentice Lvl 7 | 518:10 | 518:10 | 21871.27 | 42.21
Employee 62 | Health & Safety Coordinator | 237:00 | 237:00 | 15506.57 | 65.43
Employee 63 | Apprentice Lvl 3 | 283:30 | 283:30 | 9134.52 | 32.22
Employee 64 | Apprentice Lvl 1 | 643:40 | 643:40 | 20927.67 | 32.51
Employee 65 | Foreman Lvl 1 | 272:30 | 272:30 | 21674.75 | 79.54
Employee 66 | Apprentice Lvl 3 | 32:30 | 32:30 | 1680.9 | 51.72
Employee 67 | Apprentice Lvl 8 | 912:20 | 912:20 | 50077.94 | 54.89
Employee 68 | Apprentice Lvl 1 | 571:00 | 571:00 | 21615.58 | 37.86
Employee 69 | Apprentice Lvl 4 | 654:45 | 654:45 | 35530.73 | 54.27
Employee 70 | Apprentice Lvl 4 | 153:30 | 153:30 | 5875.98 | 38.28
Employee 71 | Apprentice Lvl 5 | 619:10 | 619:10 | 22787.82 | 36.8

## AUDIT NOTES
AUDIT NOTES: formula review of 'Template-Empty - WORK IN PROGRESS.xlsm'
Values quoted are what the original file currently calculates (20,800 plumbing hours entered, no HVAC).
# | Severity | Where (original) | What happens now | Why it matters / $ impact | How the new workbook handles it
1 | HIGH | PRJ SUMMARY D12 via P&H SUMMARY L2 (rate = PRJ INFO D42) | Bid labour = hours x $70.20, a simple average of the 5 rates (D42 = SUM(D36:D40)/5). Crew mix % is ignored. | Crew-mix weighted rate is $64.75. On 20,800 hrs the bid carries $1,460,160 vs $1,346,696 from the crew mix (+$113,464). | Labour $ = hours x SUMPRODUCT(rate, mix) on LABOUR RATES. One rate, used everywhere.
2 | HIGH | PRJ INFO H35 / H44 ($22/hr overhead) | Overhead per hour is entered but never added to cost. The only formulas that touch H35 are PRJ SUMMARY C57:C58, by mistake. | 20,800 hrs x $22 = $457,600 of overhead not in the cost. Net of item 1, labour + OH is under-costed by $344,136 before markup. | Overhead $ is its own column on every estimate line and its own column on BID SUMMARY.
3 | HIGH | P&H SUMMARY L11:L68 (rate = PRJ INFO H36) | Every plumbing line item prices labour at $53/hr (Apprentice Lvl 1-2 only), while the summary row uses $70.20. | Line items total $1,102,400; the bid total uses $1,460,160. BUDGET PLAN and the KNOWIFY export pull the $53 lines, so the field budget is $357,760 lower than what was bid. S.O.V column Y 'ADJST' plugs the gap ($411,440). | Line labour and summary labour use the same rate, so BUDGET, BID SUMMARY and SOV tie with no plug.
4 | HIGH | HVAC SUMMARY H29 and H54 (= PRJ INFO H53) | PRJ INFO H53 is an empty cell, so every HVAC line item shows $0 labour. | Any HVAC budget built from line items would have zero labour dollars. | HVAC EST uses the HVAC crew rate from LABOUR RATES, same formula as PLUMBING EST.
5 | HIGH | PRJ INFO J46:J49 | HVAC 'Cost by wage breakdown' multiplies I45 (Apprentice 1-2 hours) by each rate instead of its own row's hours. | HVAC wage breakdown is wrong as soon as HVAC hours exist. | Each row: Hours x Rate on its own row, plus a tie-out check.
6 | MED | PRJ INFO H45:H49 | HVAC rate column links to the plumbing rates D36:D40 (and is labelled 'P&H'), not the HVAC table D45:D49. | Changing an HVAC rate in D45:D49 has no effect on HVAC labels; easy to misread. | Separate HVAC crew table with its own rates and mix.
7 | MED | PRJ INFO I37 | Apprentice 3-6 hours use PRJ SUMMARY C11 (material-row hours only); the other four rows use C10 (all plumbing hours). | Once equipment or fixture hours exist, the crew mix no longer totals 100% of hours. | All rows use the same total-hours cell.
8 | HIGH | PRJ SUMMARY C57, C58 | Supervision months for Ventilation and A/C point to PRJ INFO H35 (the $22 overhead) instead of H43 (HVAC duration). | Supervision would be charged for 22 months instead of 24. | Supervision qty links to INPUTS HVAC duration.
9 | MED | PRJ SUMMARY row 59 (Supervision - Office) | $7,500/month x 24 months = $180,000 (+15% = $207,000) is allocated 100% to Plumbing, using the HVAC duration. | Plumbing looks $207,000 more expensive than it is; HVAC looks cheaper. Confirmed this is a real job cost (dedicated PM), separate from the $22/hr overhead. | Kept as 'Office Project Manager'. Auto-splits by direct cost across divisions (or set your own %).
10 | HIGH | PRJ SUMMARY M55:T79 ("50-50 Div's" split) | GC split formulas divide by C4+C5 with no IFERROR. With no HVAC entered they return a divide-by-zero (DIV/0) error. | PRJ SUMMARY F6, G6, J6, W6 and J7 all show DIV/0 errors, so the grand total breaks on any plumbing-only job. | Allocation uses % inputs or an IFERROR-guarded direct-cost share. No divide-by-zero.
11 | MED | S.O.V B1, AC1, M2:M6, rows 4-5; KNOWIFY F1 | Broken references (REF errors from deleted cells) in the S.O.V; the Knowify 'ALL GOOD' indicator therefore shows a REF error. | The SOV check light can never go green, so it cannot be trusted. | New SCHEDULE OF VALUES built from BUDGET with Knowify line names and a contract tie-out check.
12 | MED | PRJ SUMMARY V2 / W2 | Contract = ROUNDUP(total, -2) + V2, where V2 is a hardcoded $1,200 'ROLL-UP'. | An unexplained $1,200 is added to the plumbing contract. | Removed. Rounding is a visible input on INPUTS.
13 | MED | PRJ SUMMARY E11:E26 (15%) | Markup on cost is applied, not margin. 15% markup = 13.0% margin. | If the company target is 15% margin, every bid is about 2 points short. | Margin entered per division; equivalent markup shown beside it.
14 | LOW | P&H SUMMARY M45; HVAC SUMMARY J29, J54 | Total-hours boxes leave out Finishing Misc hours (J37, J21, J46). | The cost box on those tabs under-reports if finishing misc hours are used. | Single hours column summed across every row.
15 | LOW | P&H SUMMARY row 26 and HVAC SUMMARY rows 13 / 37 | Condensate drains appear in both Plumbing and HVAC. | Risk of pricing the same scope twice. | Kept on both tabs, labelled 'if by Plumbing' / 'if by HVAC'. Use only one.
16 | OK | PRJ INFO E40 (Foreman & PM 14%) and PRJ SUMMARY rows 55-58 | Foreman & PM time is in the crew mix and supervision is also a GC line. | Reviewed with estimator: these are separate costs, not a double count. | Both kept: crew mix on LABOUR RATES, supervision on SUBS & GC.
17 | LOW | BUDGET PLAN J1 | Supervision/PM wage hardcoded at $50/hr, a fourth labour rate in the file. | Budget supervision hours do not match the bid. | One rate source: LABOUR RATES.
18 | LOW | PRJ SUMMARY X1 / Z1 | 'PRJ DAYS' = hours / 8 is really man-days; 'MAN DAYS' = man-days / crew is really duration in days. | Labels swapped; easy to misread schedule. | Not carried over. Hours per unit shown on BID SUMMARY.
OPEN QUESTIONS FOR YOU
| 1 | Target margin per division (placeholder is 15%). Do subs carry a lower margin than self-perform work?
| 2 | Knowify's average cost per hour on 405 Marie Place was about $50.50, vs a $64.75 crew-mix rate in the template (Apprentice Lvl 1 about $40 vs $53). Does Knowify's labour cost include full burden (CPP, EI, WCB, vacation, benefits)? If not, Knowify is overstating job profit; if it does, the template rates are high.
| 3 | Materials at 26% of COGS: on 405 Marie Place, material excluding fixtures & equipment supply was 25.9% of cost, and all material about 46%. The workbook assumes your 26% means pipe, fittings and valves only. Is that right?
| 4 | Labour, subtrade and general conditions % of COGS to complete INPUTS (only material is filled).
| 5 | Takeoff import (next version): which software exports the takeoff (Bluebeam markups summary?) and can you send one sample?
ANSWERED (decisions built into this workbook)
| OK | $22/hr overhead covers all salaried staff company wide. A dedicated office project manager per job is a separate monthly cost, so the Office Project Manager GC line stays.
| OK | Field supervision GC lines are not double counted with the Foreman & PM share of the crew mix. Both stay.
| OK | Labour rates on LABOUR RATES are fully burdened (CPP, EI, WCB, vacation, benefits). No extra burden % is added.
| OK | Typical material cost is 26% of total COGS (entered on INPUTS).
| OK | Knowify export format confirmed (Job Summary report). SOV and BUDGET now use the same phase structure and line naming.
| OK | SOV keeps the split by floor, now in Knowify naming: labour by level, material supply as its own line.